**e-ScienceTalk**

Quarter 7 Report: Mar to May 2012

**EU REPORT**

|  |  |
| --- | --- |
| Document identifier: | e-ScienceTalk\_Q7report\_final |
| Date: | 25/06/2012 |
| Work package: | **WP4** |
| Lead Partner: | **EGI.eu** |
| Document Status: | **DRAFT** |
| Dissemination Level: | **PUBLIC** |
| Document Link: | https://documents.egi.eu/document/xxx |

|  |
| --- |
| Abstract  This report summarises the activities of the e-ScienceTalk project during the seventh quarter of the project, March to May 2012, including a work package summary, effort figures, metrics for the quarter, issues and plans for the next quarter. |

1. Copyright notice

Copyright © Members of the e-ScienceTalk collaboration, 2011. See www.e-sciencetalk.eu for details of the e-ScienceTalk project and the collaboration. E-ScienceTalk is a project co-funded by the European Commission as an Support Action within the 7th Framework Programme. E-ScienceTalk began in September 2010 and will run for 33 months. This work is licensed under the Creative Commons Attribution-Noncommercial 3.0 License. To view a copy of this license, visit http://creativecommons.org/licenses/by-nc/3.0/ or send a letter to Creative Commons, 171 Second Street, Suite 300, San Francisco, California, 94105, and USA. The work must be attributed by attaching the following reference to the copied elements: “Copyright © Members of the e-ScienceTalk Collaboration, 2011. See www.e-sciencetalk.eu for details of the e-ScienceTalk project and the collaboration”. Using this document in a way and/or for purposes not foreseen in the licence, requires the prior written permission of the copyright holders. The information contained in this document represents the views of the copyright holders as of the date such views are published.

1. Delivery Slip

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Name** | **Partner/Activity** | **Date** |
| **From** | Catherine Gater | EGI.eu/WP4 | 08/6/2012 |
| **Reviewed by** | **Moderator:**  **Reviewers:** Project team | Various | 25/06/2012 |
| **Approved by** | **PMB** |  | 25/06/2012 |

1. Document Log

|  |  |  |  |
| --- | --- | --- | --- |
| **Issue** | **Date** | **Comment** | **Author/Partner** |
| 1 | 08/06/2012 | First draft | Catherine Gater/EGI.eu |
| 2 | 25/06/2012 | Final draft | Catherine Gater / EGI.eu |
| 3 |  |  |  |

1. Application area

This document is a formal deliverable for the European Commission, applicable to all members of the e-ScienceTalk project and its beneficiaries and collaborating projects.

1. Document amendment procedure

Amendments, comments and suggestions should be sent to the authors.

1. PROJECT SUMMARY

Over the last 10 years, the European Commission and governments have invested substantial funds in distributed computing infrastructures. Scientists have access to state-of-the-art computational and data resources located around the world, putting European research into a leading position to address the greatest challenges facing us today, such as climate change, pandemics and sustainable energy. The advent of the European Grid Infrastructure, combined with the blurring of boundaries between grids, clouds, supercomputing networks and volunteer grids, means that a clear consistent source of information aimed at non-experts is now more important than ever, through dissemination projects such as e-ScienceTalk, that cross national boundaries.

**Objectives**:

* e-ScienceTalk will build on the achievements of the GridTalk project in bringing the success stories of Europe’s e-Infrastructure to policy makers in government and business, to the scientific community and to the general public.
* e-ScienceTalk will work with EGI-InSPIRE and other collaborating projects to expand the scope of the existing GridTalk outputs, and to report on the interactions of grids with e-Infrastructures such as cloud computing and supercomputing.
* The project will explore options for the sustainability of e-ScienceTalk’s products.
* e-ScienceTalk will produce a series of reports aimed at policy makers to disseminate key policy issues underpinning grid and e-Infrastructure development in Europe. The project will also coordinate e-concertation activities.
* The GridCafé, GridCast and GridGuide suite of websites will cover new topics and explore novel web technologies; they will integrate closely with GridPP’s Real Time Monitor, combining live views of grid activity with the human aspects of computing.
* The growing weekly publication, International Science Grid This Week (iSGTW) will bring news and events to the existing and potential e-Science community.

1. EXECUTIVE SUMMARY

This report covers the seventh quarter of the e-ScienceTalk project, March to May 2012. This document reports on the activities of the seventh quarter in each work package, summarises any issues raised and previews plans for the final quarter of PY2. The management report includes summary effort figures, the expected spending profile for the next period and includes the project metrics for each work package.

The outputs from WP1 Policy, Impact and Sustainability, have been in events, e-ScienceBriefings and GridCasts, producing the seventh e-ScienceBriefing D1.2.7 which covered the topic of visualisations. In Q7, WP2 ran 4 full or mini GridCasts at events in Europe. WP2 also worked on the Real Time Monitor. International Science Grid This Week was sent to just over 8000 subscribers by email by WP3, and increased social media followers. An iSGTW promotional poster was produced in collaboration with WP2 for display at the EGI Community Forum 2012 in Munich, along with GridCast posters for the same meeting. WP3 has continued to publish iSGTW, with 13 issues produced during the quarter.

The e-Science impact reporter at QMUL recruited during Q6, joined the project full time on 27 February. During the interim period, tasks and responsibilities were carried out by the Dissemination Officer (0.8 FTE), and this additional support has continued to the end of May. WP1 continues to work on achieving a good balance of information and contributions from collaborating projects in the e-ScienceBriefings. In WP3, the Asia Pacific Regional editor, Vivian Chang, left the post on 31 May and a new person is being sought at ASGC. EU Editor Jacqui Hayes left CERN at the end of March and CERN is re-recruiting to the EU editor role, and expects the new Editor to be in place at the end of the summer. The Science Writer, Adrian Giordani has been acting as interim EU Editor while the recruitment is ongoing. US Editor Miriam Boon will leave the publication in June. Fermilab are working with US colleagues to seek new funding for the iSGTW US Editor position from the National Science Foundation.

The project management report confirms that all Deliverables and Milestones have been submitted to the EC on time. Efforts are now concentrating on establishing MoUs or collaboration agreements with the ESFRI cluster projects, such as CRISP, ENVRI, BioMedBridges and DASISH. The MoU with CRISP is in negotion shortly after a presentation of e-ScienceTalk services to the CRISP Steering Committee in April 2012. One further MoU was signed with GlobalExcursion, which aims to introduce e-Infrastructures to scientific teaching in European schools. Effort reporting for the seventh quarter is lower than expected, with estimated effort at 76% of the planned effort.

TABLE OF CONTENTS

1 Introduction 7

2 main achievements 8

2.1 Summary 8

2.2 Work packages 8

2.2.1 WP1: Policy, impact and sustainability 8

2.2.2 WP2: GridCafé, GridGuide, GridCast 8

2.2.3 WP3: iSGTW 9

2.3 Issues and mitigation 10

2.3.1 WP1: Policy, impact and sustainability 10

2.3.2 WP2: Gridcafé, GridGuide, Gridcast 10

2.3.3 WP3: iSGTW 10

2.4 Plans for the next quarter 11

2.4.1 WP1: Policy, impact and sustainability 11

2.4.2 WP2: Gridcafé, GridGuide, Gridcast 11

2.4.3 WP3: iSGTW 12

3 Consortium management 13

3.1 Summary 13

3.2 WP4: Management 13

3.2.1 Project management 13

3.2.2 Milestones and Deliverables 13

3.2.3 Consumption of effort 14

3.2.4 Overall financial status 16

3.2.5 WP4: Management issues and mitigation 16

3.2.6 WP4: Plans for the next quarter 17

4 project metrics 18

4.1.1 WP1: Policy, impact and sustainability 18

4.1.2 WP2: Gridcafé, GridGuide, Gridcast 19

4.1.3 WP3: iSGTW/Digital Scientist 20

4.1.4 WP4: Management 21

5 conclusion 22

6 References 23

# Introduction

This document reports on the activities of the seventh quarter in each work package for e-ScienceTalk, covering the e-ScienceBriefings, the GridCafé, GridCast and GridGuide, as well as the Real Time Monitor and International Science Grid This Week. The report also summarises any issues raised or addressed during the seventh quarter, and previews plans for Q8. The management report includes summary effort figures for the quarter and includes the project metrics for each work package.

# main achievements

## Summary

This section summarises the main achievements by each work package during the seventh quarter of the project.

## Work packages

### WP1: Policy, impact and sustainability

E-ScienceTalk also launched the seventh e-ScienceBriefing on the topic of visualisation [R1]. This policy document D1.2.6, covered a number of projects and was launched at ISGC2012 in Taipei. The document was also emailed to the EGI dissemination mailing list, as well as the. e-IRG Board members. To aid distribution, a new e-ScienceTalk briefing mailing list was set up in September 2011, which allows people to subscribe to receive the publication. This currently has around 112 members. Feedback on D1.2.6 was gathered using a Zoomerang survey.

The e-ScienceTalk team has also attended a number of policy related events during the quarter, including outGRID ITU High Level workshop, Citizen CyberScience Summit, CloudScape IV and ISGC2012. A GridCast or mini GridCast was also held at each event.. At these events and others attended by WP2/WP3, copies of the new Research Networks and Asian-Pacific Special Issue briefings have been distributed.

### WP2: GridCafé, GridGuide, GridCast

WP2 has worked on e-ScienceTalk’s suite of interactive websites, Gridcafé, GridCast and GridGuide, as well as the main project website and the Real Time Monitor.

During the sixth quarter, the following work was carried out.

**GridCafé**

* The Volunteer Garage area of the website was published live, and launched at the ISGC’12 event in Taipei.
* The 3-D pilot of the GridCafé in collaboration with Virtus / New World Grid is now available through the e-ScienceCity website. Graphics from the 3D version are being used to brand the corresponding areas on the website eg Cloud Lounge, Volunteer Garage.

**GridCast**

* GridCasts were held at the outGRID ITU High Level workshop in Geneva, the Citizen CyberScience in London, CloudScape IV in Brussels and ISGC2012 in Taipei.

**GridGuide**

* An additional 25 sites were added to the GridGuide, bringing the total to 57 sites in total, 36 in Europe and 21 in Africa, the US and Asia.
* A competition was carried out to encourage existing sites to update and expand their GridGuide pages. In response 4 sites notified us of updated content and were entered into the competition.
* WP4 is working on MoUs with collaborating projects such SAGrid and REUNA to increase the number of non-European sites.

**Real Time Monitor**

* QMUL worked with the PANDA team at CERN and ATLAS data is now published to the RTM, showing these jobs in the standard version.
* The GridCast team displayed the RTM at events attended by e-ScienceTalk, including ISGC’12.

### WP3: iSGTW

Weekly issues of iSGTW were produced, 11 in total, including articles, links, images, videos, jobs, events and announcements. The new publication was marketed and promoted at events attended by the e-ScienceTalk team during the quarter, such as ISGC in Taipei, CCC Summit in London, Cloudscape in Brussels, IEEE eScience2011, OutGrid high-Level meeting in Geneva and LIFT12 in Geneva. Posters were designed in collaboration with WP2, and these were displayed at booths run by EGI and e-ScienceTalk at ISGC and CCC Summit.

Top stories during Q6 included “The Tevatron’s enduring computing legacy,” with 5689 views, “The Royal Society opens up permanently, 5295 views and “Emerging technology2012-2040” with 1791 views. The top two stories were picked up by Slashdot and Reddit, respectively. Because of a scheduled Tweet function, the iSGTW can now promote stories in all time zones, leading to an overall increase for all stories and an increase in followers on Twitter, now at 922 followers. Google Analytics data also shows that visitors who are intentionally looking for content from iSGTW stay longer on the site.

One meeting of the iSGTW Advisory Board was held during the quarter, in February, by telco. The Asia Pacific Regional editor, Vivian Chang, has been supplying stories to iSGTW and covered the ISGC 2012 event in Taipei in February. EU Editor Jacqui Hayes reported that she will be leaving CERN during the next quarter in March. CERN will seek to re-recruit to the EU editor role, but does not expect a new Editor to be in place until the summer. The Science Writer, Adrian Giordani, will act as interim EU Editor while the recruitment is ongoing. Fermilab also reported that OSG funding for the US Editor post at Fermilab will cease at the end of March. US Editor Miriam Boon will also be leaving the publication, and Fermilab will explore extending her funding for 2 months after the end of March. Beyond March, Fermilab will work with US colleagues to seek new funding for the iSGTW US Editor position from the National Science Foundation. QMUL is working on moving the hosting of the iSGTW website from the US to servers in the UK, with transfer of the email addresses from Tilted Planet. Xenomedia will continue to maintain the website day to day up until September 2012, when the US funding for the iSGTW website from Fermilab will then cease.

## Issues and mitigation

### WP1: Policy, impact and sustainability

One issue foreseen for WP1 is:

* To ensure a good balance of information and contributions from collaborating projects in the e-ScienceBriefings.

WP1 is working to mitigate this issue through developing collaborations and MoUs such as EUDAT (January 2012), and by liaising with the policy teams in projects such as EGI-InSPIRE and e-IRG. WP1 is exploring dissemination opportunities with newer projects ESFRI such as BioMedBridges, CRISP and Discover the Cosmos.

* To ensure that the next e-ScienceBriefing (D1.2.6) is released in a timely way.

Due to staff recruitment, D1.2.6 was submitted in PM18 instead of PM17. However, the briefing was available for distribution at the ISGC’12 event in Taipei as planned.

### WP2: Gridcafé, GridGuide, Gridcast

For WP2, the following issues have been reported in previous quarters:

* Adding Russian, Chinese and other non-Roman languages to the GridCafé database.
* Displaying jobs from other, non-gLite sources in the RTM.

In order to support adding Russian, Chinese and other non-Roman translations of the GridCafé, separate html sites will continue to be needed, as these are not supported by the content management system.

The RTM is exploring adding additional types of data to the interface including data transfers on the GÉANT network layer.

### WP3: iSGTW

In WP3, the following issue has been reported in previous quarters:

* Staff shortage due to the departure of US Editor Miriam Boon, and EU Editor Jacqui Hayes during the next quarter.

The EU Science Writer will act as interim EU Editor while CERN re-recruits. Fermilab will supplement the OSG funding to keep US Editor on board while CERN is recruiting, and will seek future funding from an alternative source..

## Plans for the next quarter

This section outlines for the plans for each work package during the next quarter, March 2012 to May 2012.

### WP1: Policy, impact and sustainability

During Q7, a seventh e-ScienceBriefing will be produced and circulated covering the topic of ‘Visualisations: science and modelling’ (D1.2.7). This policy briefing will explore projects such as WeNMR, and will be distributed at events attended by the e-ScienceTalk project and also by email.

WP1 has also developed a questionnaire to solicit feedback from e-ScienceBriefings subscribers, to determine the briefings’ value and to poll readers on content for future editions. An e-ScienceTalk Twitter strategy has been developed to engage our readers in conversations. WP1 plans to expand our mailing list in the next quarter, and to add a ‘Share This’ function to make it easier for people to share and pass on the briefings.

WP1 will also work towards innovation in the content of the e-ScienceBriefings, and ideas for future briefings include open Science (e.g. ScienceSoft, openAIRE, exascale), future computing and knowledge transfer to industry.

WP1 will continue to identify policy related events (e-IRG workshop, Copenhagen and ICRI’12 Copenhagen) to attend and distribute materials, and to demonstrate the GridGuide and Real Time Monitor.

### WP2: Gridcafé, GridGuide, Gridcast

For WP2, a number of developments are planned for the sixth quarter.

* **GridCafé**
  + Progress the Russian translation for the GridCafé.
  + Work on the HPC Tower area of the e-ScienceCity website.
  + Build the People Bay, Communications and News areas of the 3D website to feed into the corresponding areas on e-ScienceCity.
  + Gather feedback on the e-ScienceCity website and feed this back into the development process.
* **GridCast** 
  + Small GridCasts are planned for the HealthGrid’12, ICRI’12 and CRISP events
  + Major GridCast from the EGI Community Forum 2012 in Munich, 26-30 March.
* **GridGuide**
  + Liaise with EGI.eu and the National Grid Initiatives to include them on the site to increase the number of sites featured.
* **RTM**
  + Work with GÉANT to publish traffic on the network layer to the website as an additional layer.
  + Publicise the new logo for the RTM and review the website.
  + Streamline the user interface to increase the usability of the RTM.
  + Monitor the impact of the upgrade of WorldWind 1.4

### WP3: iSGTW

For the next quarter, as well as publishing weekly issues of the publication itself, iSGTW will continue to build its Twitter following, including advertising the announcements on Twitter. iSGTW will continue to build on the connections with XSEDE and also reach out to PRACE. The US partners will seek a new source of funding for a US-based editor, and CERN will commence the re-recruitment process for the EU editor. iSGTW will also aim to increase subscriptions by following up media partnerships with organiser of events outside the existing readership areas, such as HealthGrid’12 in Amsterdam.

# Consortium management

## Summary

This section outlines the consortium management activities during the quarter, carried out by WP4 the management work package.

## WP4: Management

### Project management

The weekly project team meetings continued during the sixth quarter. A face to face all hands meeting was held at CERN on January 17 for all project team members. This was combined with a PMB telcon meeting to discuss the outcome of the first year review report, received on December 19, 2011, including strategies for implementation of the reviewers’ recommendations. A plan for meeting these recommendations was agreed, including an increased focus on tracking and measuring the impact of the project’s products through metrics, a more structured programme for gathering of feedback and monitoring of the traffic flow between e-ScienceTalk’s products.

Collaboration efforts are now concentrating on establishing MoUs or collaboration agreements with the ESFRI projects, such as CRISP, ENVRI, BioMedBridges and DASISH. A promotional leaflet outlining e-ScienceTalks services and impact was produced for distribution to this audience, including presentations at a CRISP dissemination meeting at CERN.

### Milestones and Deliverables

**Table 1: Quarter 7 Deliverables**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Del. no.** | **Deliverable name** | **WP no.** | **Nature** | **Due (PM)** | **Delivery date**  **(PM)** | **Status** |
| D1.2.7 | e-ScienceBriefings | 1, 2 | R | 20 | 20 | Completed |

**Table 2: Quarter 7 Milestones**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Milestone number** | **Milestone name** | **WP no.** | **Due (PM)** | **Delivery date (PM)** | **Status** |
| MS10.7 | PMB meetings | 4 | 19 | 19 | Completed |

**Table 3: Quarter 8 Deliverables**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Del. no.** | **Deliverable name** | **WP no.** | **Nature** | **Due (PM)** | **Delivery date**  **(PM)** | **Status** |
| D1.2.8 | e-ScienceBriefings | 1, 2 | R | 23 |  | In progress |
| D1.4 | Annual impact and sustainability report on e-ScienceTalk products | 1 | R | 23 |  | In progress |
| D2.3 | Annual upgraded version of RTM | 2 | O | 23 |  | In progress |
| D3.5 | Report on survey of iSGTW readers and annual metrics | 3 | R | 24 |  | In progress |
| D4.4 | Annual report on feedback and metrics | 4 | R | 24 |  | In progress |

**Table 4: Quarter 8 Milestones**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Milestone number** | **Milestone name** | **WP no.** | **Due (PM)** | **Delivery date (PM)** | **Status** |
| MS4 | GridCasts | 2 | 22 |  | In progress |
| MS10.8 | PMB meetings | 4 | 22 |  | In progress |
| MS7 | Posters and marketing materials | 3, 2 | 23 |  | In progress |
| MS14 | Dissemination materials | 4 | 24 |  | In progress |

### Consumption of effort

A summary of the effort consumption by each partner in each work package is included below. Unfunded effort is included where relevant. A summary of the percentage effort delivered in Q7 is included at the end of this section.

#### Overall effort figures per work package

**Table 5: Overall effort achieved in Q7 in PMs (view 1)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package** | **Mar** | **Apr** | **May** | **Total** | **Year plan** | **Linear Q plan** | **Y1 achieved** | **Q5 % achieved** | **Q6 % achieved** | **Q7 % achieved** |
| WP1 | 1.75 | 1.39 | 1.00 | 4.14 | 46 | **4.2** | **92%** | 104% | 50% | 99% |
| WP2 | 1.56 | 1.22 | 1.19 | 3.97 | 64 | **5.8** | **75%** | 90% | 61% | 68% |
| WP3 | 2.25 | 0.75 | 0.72 | 3.72 | 52 | **4.7** | **121%** | 122% | 78% | 79% |
| WP4-M | 0.42 | 0.44 | 0.39 | 1.25 | 17 | **1.5** | **113%** | 111% | 71% | 83% |
| WP2-UNF | 0 | 0 | 0 | 0 | 8 | **0.7** | **0%** | 0% | 0% | 0% |
| WP4-UNF | 0.06 | 0.06 | 0.06 | 0.18 | 5 | **0.5** | **18%** | 40% | 12% | 36% |
| **Total** | **6.04** | **3.86** | **3.36** | **13.26** | **192** | **17.5** | **90%** | **98%** | **60%** | **76%** |

#### Overall, the effort figures for Q6 are at 60% for the quarter, significantly lower than for Q5. This is partly due to the holiday period, and partly due to non-reported effort in WP2. Also, WP1 was understrength due to the Grid Impact Reporter leaving in November 2011 before her replacement took up the post at QMUL. There has been no WP2 unfunded activity reported.

#### Overall effort figures per partner

**Table 6: Overall effort achieved in Q7 in PMs (view 2)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Partner** | **Mar** | **Apr** | **May** | **Total** | **Year plan** | **Linear Q plan** | **Y1% achieved** | **Q5 % achieved** | **Q6 % achieved** | **Q7% achieved** |
| **CERN** | 2.33 | 1.00 | 0.78 | 4.11 | 67 | **6.1** | **90%** | 105% | 78% | 67% |
| **APO** | 1.13 | 0.83 | 0.89 | 2.85 | 34 | **3.1** | **110%** | 87% | 61% | 92% |
| **QMUL** | 2.13 | 1.58 | 1.31 | 5.02 | 47 | **4.3** | **80%** | 107% | 60% | 117% |
| **IMPERIAL** | 0 | 0 | 0 | 0 | 26 | **2.4** | **80%** | 70% | 3% | 0% |
| **EGI.eu** | 0.41 | 0.44 | 0.39 | 1.24 | 18 | **1.6** | **110%** | 112% | 71% | 78% |
| **Total** | **6.00** | **3.85** | **3.37** | **13.22** | **192** | **17.5** | **90%** | **98%** | **60%** | **76%** |

Q6 represents 27% of the elapsed time of the project. The total overall effort figures for the sixth quarter are at 60% of expected for the project as a whole. CERN effort is lower compared to the plan this quarter but broadly on track overall. APO’s effort in Q5 is significantly lower than planned at 61%, due to currently unreported effort which will need to be adjusted in future quarters. QMUL effort is significantly lower than planned due to the staff recruitment process in January and should improve in future quarters. Imperial effort is still decreased compared to the plan at 3% and this is due to the non-reporting of funded and unfunded effort. The work has been provided according to the plan but the effort will need to be adjusted after the end of the quarter. EGI.eu effort is slightly lower than planned due to the holiday period.

### Overall financial status

The expenditure for the second year of the project is expected to follow the profile outlined below. Financing will be distributed to partners at the end of Year 1 based on the accepted Form C costs.

**Table 7: Expected expenditure profile Year 2**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Partner** | **WP1** | **WP2** | **WP3** | **WP4** | **Total** | **2nd Year** |
| EGI.eu |  |  |  | 187,694 | 187,694 | 68,252 |
| QMUL | 223,513 | 56,858 | 40,627 |  | 320,998 | 116,727 |
| APO | 28,088 | 154,882 | 28,088 |  | 211,057 | 76,748 |
| Imperial |  | 114,181 |  |  | 114,181 | 41,520 |
| CERN | 69,164 | 77,562 | 319,344 |  | 466,070 | 169,480 |
| **Total** | **320,764** | **403,485** | **388,057** | **187,694** | **1,300,000** | **472,727** |

**Table 8: Estimated Personnel expenditure Q7**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package** | **Mar** | **Apr** | **May** | **Cumul Direct** | **Cumul Indirect** | **Cumul Eligible** | **Q7**  **Estimated**  **Funding** |
| WP1 | 7,710 | 6,110 | 4,385 | 18,204 | 3,641 | 21,845 | **19,479** |
| WP2 | 7,557 | 6,204 | 5,875 | 19,636 | 3,927 | 23,563 | **21,010** |
| WP3 | 13,054 | 4,066 | 4,166 | 21,287 | 4,257 | 25,544 | **22,777** |
| WP4-M | 3,407 | 3,643 | 3,302 | 10,351 | 2,070 | 12,422 | **11,076** |
| WP2-UNF | 0 | 0 | 0 | 0 | 0 | 0 | **n/a** |
| WP4-UNF | 233 | 233 | 233 | 0 | 0 | 0 | **n/a** |
| **Total** | **31,961** | **20,256** | **17,961** | **70,178** | **14,036** | **84,214** | **74,341** |

In line with the under spending of the person months planned, the costs of the personnel are lower than the projected estimates. The partners have spent in total 74keuro during the quarter; 129keuros were (linearly) forecast over a 3-month period.

### WP4: Management issues and mitigation

For WP4, a number of additional issues arose in Q6:

* High travel costs for some work packages and uneven spending of travel budgets during PY1.
* Identification of a new funding steam for the US Editor post, together with a new host institution
* Recruitment to the EU Editor post and coverage of the resulting shortfall in effort over the summer period.
* Identification of funding for the costs of day to day maintenance of the iSGTW website by Xenomedia, once Fermilab funding ceases.

Travel costs have continued to be mitigated as much as possible in Q6 by planning and booking travel as early as possible. Financial assistance was received from ASGC in order to support the travel costs for team members travelling to ISGC2012.

The project manager is working with the US colleagues at OSG to resolve the funding issues, liaising with CERN on the recruitment for the new EU Editor and discussing budget reallocation from existing e-ScienceTalk project funds with DG-INFSO.

### WP4: Plans for the next quarter

The project manager is working with the US colleagues at OSG and Indiana University on a proposal for NSF funding, including supplying supporting statements for iSGTW to NSF and soliciting support from DG-INFSO. The 2nd Year amendment has been adjusted to include funds for freelance writers during the summer period while the EC Editor is recruited. A further 8K Euros will be allocated to maintenance of the iSGTW website from September 2012 to the end of the project.

# project metrics

Project metrics have been revised in D4.3 *Annual report on feedback and metrics* [R2]. The revised metrics are now being tracked and are summarised for each work package below. Project level metrics are indicated in bold type.

### WP1: Policy, impact and sustainability

**Table 11: Metrics for Work Package 1**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Metric no.** | **Description** | **Comments** | **Q5** | **Q6** | **Q7** |
| **1.1** | **Projects covered** | **In the e-ScienceBriefings** | **19** | **18** | **19** |
| **1.2** | **Reports and briefings published** | **In print or by email** | **1** | **1** | **1** |
| **1.3** | **Countries where reports or briefings are distributed** | **In print or by email** | **27** | **27** | **32** |
| 1.4 | Policy articles published | In print or online | 2 | 2 | 2 |
| 1.5 | Printed policy reports circulated per briefing | To policy makers | 600 | 140 | 100 |
| 1.6 | Policy events organised | Number organised | 1 | 0 | 1 |
| 1.7 | Attendees at e-ScienceTalk organised policy events | Number of delegates | 151 | 0 | 0 |
| 1.8 | Policy events attended by e-ScienceTalk | Number attended, physically or virtually | 2 | 2 | 2 |
| 1.9 | Delegates at policy events attended by e-ScienceTalk | Number of delegates at events attended. | 100 | 160 | 300 |
| 1.10 | Downloads of policy documents | Measured from the e-ScienceTalk web site | 2098 | 3.055 | 4,359 |

### WP2: Gridcafé, GridGuide, Gridcast

**Table 12: Metrics for Work Package 2**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Metric no.** | **Description** | **Comments** | **Q5** | **Q6** | **Q7** |
| **2.1** | **Sites on GridGuide** | **Number of sites included** | **40** | **57** | **57** |
| **2.2** | **Bloggers contributing to GridCasts** | **Average number of bloggers on GridCast** | **5** | **5** | **5** |
| **2.3** | **GridCasts per year** | **Including major and mini GridCasts** | **3** | **4** | **4** |
| 2.4 | New areas of GridCafé | Covering topics other than grid computing | 1 | 1 | 0 |
| 2.5 | Change in unique visitors to the GridCafé website | From Google Analytics | 2384 | 2064  (-14%) | 2511  (+18%) |
| 2.6 | Ratio of page views to visitors for the GridCafé website | From Google Analytics | 1,46 | 3.3 | 4.61 |
| 2.7 | Number of bloggers for GridCast | Total number of bloggers | 14 | 12 | 12 |
| 2.8 | Blog entries on GridCast | Total number | 45 | 45 | 53 |
| 2.9 | Podcasts on GridCasts | Total number | 10 | 7 | 13 |
| 2.10 | Unique visitors to the GridCast (% new) | From Google Analytics | 69% | 77.59% | 72.9% |
| 2.11 | Length of time spent on the GridCast | From Google Analytics | 1:33 | 1:20 | 1:35 |
| 2.12 | EU sites on GridGuide | European based sites | 28 | 36 | 36 |
| 2.13 | Non-EU sites on GridGuide | Non-European located sites | 12 | 21 | 21 |
| 2.14 | Unique visitors to the GridGuide | From Google Analytics | 385 | 389 | 420 |
| 2.15 | Page views of the GridGuide | From Google Analytics | 625 | 614 | 637 |
| 2.16 | GridGuide sites on RTM | Total number | 34 | 34 | 59 |
| 2.17 | Countries in the RTM | Total number[[1]](#footnote-1) | 64 | 64 | 64 |
| 2.18 | Numbers of delegates at events demo-ing the RTM | Including events attended by collaborating projects demo-ing the RTM | 10,540 | 0 | 890 |

### WP3: iSGTW/Digital Scientist

**Table 13: Metrics for Work Package 3**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Metric no.** | **Description** | **Comments** | **Q5** | **Q6** | **Q7** |
| **3.1** | **iSGTW subscribers** | **Registered in the database** | **8,190** | **8,162** | **8,173** |
| **3.2** | **Articles on European projects** | **Based on EU funded projects** | **28** | **27** | **30** |
| **3.3** | **Projects in the iSGTW/GridCafé resources section** | **Total number** | **134** | **134** | **134** |
| **3.4** | **iSGTW printed materials distributed** | **At events attended by e-ScienceTalk or by collaborating projects** | **560** | **600** | **610** |
| 3.5 | Issues published | Issued by email to subscribers each week and posted on the website | 13 | 11 | 13 |
| 3.6 | US articles published | Based on US projects | 34 | 28 | 36 |
| 3.7 | Worldwide articles published | Based on non US or EU projects | 9 | 4 | 11 |
| 3.8 | Unique visitors to the website | From Google Analytics | 43,273 | 43,228 | 46,665 |
| 3.9 | Page views of the website | From Google Analytics | 80,050 | 77,736 | 89,626 |
| 3.10 | Countries or territories visiting the iSGTW website | From Google Analytics | 166 | 173 | 165 |
| 3.11 | Marketing materials distributed | In print or by email or at events | 560 | 600 | 610 |
| 3.12 | Survey responses | Through Zoomerang survey tool | No Survey Issued | No Survey Issued | No Survey Issued |
| 3.13 | Social media subscribers | On Twitter and Facebook | 1,093 | 1,410 | 1,623 |
| 3.14 | Time spent on the site per visit | From Google Analytics | 1 minute and 37 seconds | 1 minute and 31 seconds | 1 minute and 38 seconds |
| 3.15 | Stories shared on social media | Via all social media channels | Not collected | Not collected | No collected |

### WP4: Management

**Table 14: Metrics for Work Package 4**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Metric no.** | **Description** | **Comments** | **Q5** | **Q6** | **Q7** |
| 4.1 | Deliverables submitted | By email and online | 2 | 1 | 1 |
| 4.2 | Milestones agreed | By email and online | 3 | 6 | 1 |
| 4.3 | Late Deliverable and Milestones | Submitted or agreed after the date agreed with the EC | 0 | 2 | 0 |
| 4.4 | e-ScienceTalk materials produced | Included printed materials, pens, banners etc | 0 | 1 poster | 0 |
| 4.5 | Unique visitors to the e-ScienceTalk website | From Google Analytics | 533 | 633 | 543 |
| 4.6 | Referrals from the e-ScienceTalk website to other e-ScienceTalk sites | From Google Analytics | 0 | 189 | 233 |
| 4.7 | Media releases issued | Issued via Alphagalileo and by email | 0 | 1 | 2 |
| 4.8 | Press cuttings | Measured by Google Alerts | 0 | 0 | 4 |
| 4.9 | Events attended | By e-ScienceTalk project team | 9 | 6 | 7 |
| 4.10 | Social media subscribers | On Twitter | 1559 | 1663 | 1778 |
| 4.11 | Media partnerships at events | Number of events with e-ScienceTalk as media partners | 2 | 2 | 1 |
| 4.12 | Number of MoUs signed | With collaborating projects | 2 | 2 | 1 |

# conclusion

The seventh quarter for e-ScienceTalk has seen a range of outreach activities and launches. Expenditure of costs and effort are slightly below planned for the quarter. All Deliverables and Milestones have been completed and submitted on time apart from 1 Deliverable and 1 Milestone, an e-ScienceBriefing due to staff shortage and a PMB meeting due to PMB member availability, both of which were submitted the following month.

# References

|  |  |
| --- | --- |
| R2 | D1.2.7 e-ScienceBriefing  <https://documents.egi.eu/document/1114> |
| R2 | D4.3 Annual Report on Feedback and Metrics  <https://documents.egi.eu/document/792> |

1. <http://gridportal-ws01.hep.ph.ic.ac.uk/dynamic_information/egee-locations.xml> [↑](#footnote-ref-1)