WP5: Work Progress of Scenario 1.3

Authors:

Eva Toller (National Archives of Sweden, RA)

……

| Project co-funded by the European Commission within the ICT Policy Support Programme |
| --- |
| Dissemination Level |
| P | Public | ??? |
| C | Confidential, only for members of the consortium and the Commission Services | ??? |

Revision History

| Revision | Date | Author | Organisation | Description |
| --- | --- | --- | --- | --- |
| 1.0 | 20130423 | Eva Toller | RA | First draft |
|  |  |  |  | This document is continually changed, and new revisions are only created when and if the major structure of the document is changed. |

Work Progress

For the numbering of backlog IDs, see https://docs.google.com/spreadsheet/ccc?key=0AuKxnKM_liK-dGpqcGV6ZkVScDhGRjFzZ3gybWp0eVE#gid=0

For the numbering of activities, see DCH-RP_WP5_Scen-1-3_ID-56.doc on https://documents.egi.eu/public/ShowDocument?docid=1697

Finished tasked are marked with green.

| Backlog ID | Activity # | Activity description | Star-ted | Sta-tus | Description of work in progress | Depen-dencies | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1a | Investigate the existing tools that may be applicable for this scenario… | 2013-05-13 | Finished | ROND (Riksarkivet Open Data) will be used to de-identify “Filmregistret” (see also 3a). 2013-05-20 Selected two high-priority and two low-priority tools to be tested locally for this scenario. | 1b (partly) | Tests finished for: ROND. ----------- There are more tools that can be tested if the tests of these four tools do not give acceptable results. |
|  | 2a | Investigate all preparations that must be done to make usage of SweGrid and Swestore… | 2013-04-29 | In progress | 2013-04-29 The first impression is that SweGrid/SweStore will be very hard to use for non-scientist and non-technical persons. However, there is an ARC Graphical Client that may simplify procedures (this will be tested). | 2b (also dependent on 1b) | An activity 2e is added to evaluate the ARC Graphical Client. If it is considered to be too hard to use, activities 2b – 2d may be skipped and another provider may be investigated instead. |
|  | 2e | Test and evaluate the ARC Graphical Client | 2013-04-30 | In progress | 2013-04-30: Downloaded and unpacked arc-gui-clients-0.4.3-Source.tar.gz (using 7-Zip). | 2b |  |
|  | 3a | Obtain permission from the Electronic Archives section… | 2013-04-29 | Finished | 2013-04-29 Wrote to the Electronic Archives section (ElArk) to obtain permission for using “Filmregistret” and “Linnéjubiléet” outside the Preservation Net. 2013-04-30: Got permission from ElArk to use these two datasets. Made a joint decision to de-identify “Filmregistret” of personal data. 2013-05-02: suggested to ElArk what specific personal data that should be de-identified (censors and technicians, but not directors and actors). Got OK from ElArk. 2013-05-27: Documented the test data in DCH-RP_WP5_Scen-1-3_ID-51.doc | 3d (also dependent on 3c) |  |
|  | 3b | Select a number of appropriate DjVu, jpeg, and TIFF images. | 2013-04-23 | Finished | 2013-04-23 Wrote to the person responsible for preservation of Images& Audio and asked for help to select suitable images. 2013-04-29 Obtained a sample of jpeg images from the Ljud&Bild section (Images&Audio) and selected some of them. 2013-05-16 Downloaded a sample of DjVu images from the GEORG database (http://www.riksarkivet.se/default.aspx?id=21561&refid=22519). Selected a number of DjVu images from http://www.svar.ra.se/ To download them, I first must waut for an account. 2013-05-17 Got a SVAR account and downloaded selected images. 2013-05-27: Documented the test data in DCH-RP_WP5_Scen-2-2_ID-66.doc and DCH-RP_WP5_Scen-2-2_ID-66-restricted.doc |  | Done in collaboration with Scenario 2.2. |
|  | 3c | Obtain permission from the Audio-Visual section... | 2013-05-06 | Finished | 2013-05-06: Wrote to the Audio-Visual section (L&B) to obtain permission for using a number of jpeg images and “Grundlags-utredningen” outside the Preservation Net. Got permission from L&B to use these datasets. 2013-05-27: Documented the test data in DCH-RP_WP5_Scen-1-3_ID-51.doc |  | Done in collaboration with Scenario 2.2. |
|  | 3d | Obtain permission from the legal owner of the information... | 2013-05-17 | In progress | 2013-05-17 Wrote to Karin Å-I to obtain the name(s) of the current information owner(s). 2013-05-20 Obtained permission from Kenneth Hänström (HLA) to use the digitized parchemnt archives (Pergament- och brevpapperssamlingen) |  | Done in collaboration with Scenario 2.2. |
|  | 4a | Make an inventory of the cloud archive providers (CAP) in Sweden. |  |  |  | 4c |  |
|  | 4b | Compile a list of requirements appropriate for the scenario…) |  |  |  | 4c |  |
|  | 5a | Metadata: check the status of the Swedish eARD project for the chosen file formats. |  |  |  | None |  |