WP5: Work Progress of Scenario 2.4

Authors:

Eva Toller (National Archives of Sweden, RA)

……

| Project co-funded by the European Commission within the ICT Policy Support Programme |
| --- |
| Dissemination Level |
| P | Public | ??? |
| C | Confidential, only for members of the consortium and the Commission Services | ??? |

Revision History

| Revision | Date | Author | Organisation | Description |
| --- | --- | --- | --- | --- |
| 1.0 | 20130423 | Eva Toller | RA | First draft |
|  |  |  |  | This document is continually changed, and new revisions are only created when and if the major structure of the document is changed. |

Work Progress

For the numbering of backlog IDs, see https://docs.google.com/spreadsheet/ccc?key=0AuKxnKM_liK-dGpqcGV6ZkVScDhGRjFzZ3gybWp0eVE#gid=0

For the numbering of activities, see DCH-RP_WP5_Scen-2-4_ID-72.pdf

Finished tasked are marked with green.

| Backlog ID | Acti-vity # | Activity description | Star-ted | Status | Description of work in progress | Depen-dencies | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1a | Investigate the existing dissemination tools and formats … | 2013-05-13 | Finished | 2013-05-20 Selected two high-priority and two low-priority tools to be tested locally for this scenario. |  | There are more tools that can be tested if the tests of these four tools do not give acceptable results. |
|  | 2a | Investigate all preparations that must be done to make usage of SweGrid and Swestore… | 2013-04-29 | In progress | 2013-04-29:The first impression is that SweGrid/SweStore will be very hard to use for non-scientist and non-technical persons. However, there is an ARC Graphical Client that may simplify procedures (this will be tested). |  | ARC Graphical Client is evaluated in Scenario 1.3. Postponed to Proof of Concept #2! |
|  | 3a | Obtain permission from the Electronic Archives section… | 2013-04-29 | Finished | 2013-04-29: Wrote to the Electronic Archives section (ElArk) to obtain permission for using “Linnéjubiléet” outside the Preservation Net. 2013-04-30: Got permission from ElArk to use this dataset. 2013-05-27: Documented the test data in DCH-RP_WP5_Scen-2-4_ID-68.pdf | 3b | Done in collaboration with Scenario 1.3. |
|  | 3b | Obtain permission from the legal owner of the information... | 2013-05-17 | In progress | 2013-05-17 Wrote to Karin Å-I to obtain the name(s) of the current information owner(s). 2013-06-27: wrote a reminder to Karin. She answered that she had forwarded the question to Björn A and Ann H. |  | Done in collaboration with Scenario 1.3. |
|  | 4a | Make an inventory of the cloud archive providers (CAP) in Sweden. |  | In progress |  |  | Done in collaboration with Scenario 1.3. Postponed to Proof of Concept #2! |
|  | 4b | Compile a list of requirements appropriate for the scenario… |  |  |  |  | Done in collaboration with Scenario 1.3. Postponed to Proof of Concept #2! |
|  | 5a | Register the web site archive in the archive information system… |  |  |  |  |  |
| 86 |  | Identify required local resources for scenario 2.4 | 2013-05-20 | Finished | Added four tools to be tested in PoC #1. |  | More tools may be added later. |
| 120 |  | Test WARC Tools | 2013-06-18 | In progress | 2013-06-18: started to investigate how you download WARC Tools 2013-06-19: wrote about the problems with downloading. Will do no more on this task now. 2013-08-05: Sent e-mail to Rosette and Börje for accept/reject. |  |  |
| 122 |  | Test Web Curator Tool | 2013-06-20 | In progress | 2013-06-20: downloaded the tool and the user manual. 2013-06-27: installed MySQL (an RDBMS is mandatory for Web Curator Tool). 2013-08-06: installed PostgreSQL instead of MySQL (simpler). But concluded that the installation of the total WCT environment was too complicated and the installation instructions were outdated. Sent e-mail to Rosette and Börje for accept/reject. |  |  |
| 123 |  | Test SWAT | 2013-06-24 | In progress | 2013-06-24:downloaded and unpacked SWAT. 2013-06-27: wrote some questions to Mikael Tylmad (the creator of SWAT). Got some answer and a document with installation instructions. 2013-08-05: continued with the downloading, wrote about the problems with downloading and installation. Will do no more on this task now. Sent e-mail to Rosette and Börje for accept/reject. |  |  |
| 125 |  | Obtain a test person (like the one described in scenario 2.4) | 2013-07-30 | Finished | Kristina B agreed to this. |  |  |
| 129 |  | Test HTTrack | 2013-07-30 | Finished | 2013-07-30: Downloaded and tested HTTrack on the Linné site. Sent e-mail to Rosette and Börje for accept/reject. |  |  |