**e-ScienceTalk**

Quarter 9 Report: Mar to May 2013

**EU REPORT**

|  |  |
| --- | --- |
| Document identifier: |  |
| Date: | 31/08/2013 |
| Work package: | **WP4** |
| Lead Partner: | **EGI.eu** |
| Document Status: | **FINAL** |
| Dissemination Level: | **PUBLIC** |
| Document Link: | https://documents.egi.eu/document/1924 |

|  |
| --- |
| AbstractThis report summarises the activities of the e-ScienceTalk project during the eleventh quarter of the project, March to May 2013, including a work package summary, effort figures, metrics for the quarter, issues and plans for the next quarter.  |

1. Copyright notice

Copyright © Members of the e-ScienceTalk collaboration, 2011. See www.e-sciencetalk.eu for details of the e-ScienceTalk project and the collaboration. E-ScienceTalk is a project co-funded by the European Commission as an Support Action within the 7th Framework Programme. E-ScienceTalk began in September 2010 and will run for 33 months. This work is licensed under the Creative Commons Attribution-Noncommercial 3.0 License. To view a copy of this license, visit http://creativecommons.org/licenses/by-nc/3.0/ or send a letter to Creative Commons, 171 Second Street, Suite 300, San Francisco, California, 94105, and USA. The work must be attributed by attaching the following reference to the copied elements: “Copyright © Members of the e-ScienceTalk Collaboration, 2011. See www.e-sciencetalk.eu for details of the e-ScienceTalk project and the collaboration”. Using this document in a way and/or for purposes not foreseen in the licence, requires the prior written permission of the copyright holders. The information contained in this document represents the views of the copyright holders as of the date such views are published.

1. Delivery Slip

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Name** | **Partner/Activity** | **Date** |
| **From** | Catherine Gater | EGI.eu/WP4 | 31/07/2013 |
| **Reviewed by** | **Moderator:** **Reviewers:** Project team | Various | 31/07/2013 |
| **Approved by** | **PMB** |  |  |

1. Document Log

|  |  |  |  |
| --- | --- | --- | --- |
| **Issue** | **Date** | **Comment** | **Author/Partner** |
| 1 | 31/07/2013 | ToC | Catherine Gater/EGI.eu |
| 2 | 31/07/2013 | First draft | Catherine Gater / EGI.eu |
| 3 |  |  |  |

1. Application area

This document is a formal deliverable for the European Commission, applicable to all members of the e-ScienceTalk project and its beneficiaries and collaborating projects.

1. Document amendment procedure

Amendments, comments and suggestions should be sent to the authors.

1. PROJECT SUMMARY

Over the last 10 years, the European Commission and governments have invested substantial funds in distributed computing infrastructures. Scientists have access to state-of-the-art computational and data resources located around the world, putting European research into a leading position to address the greatest challenges facing us today, such as climate change, pandemics and sustainable energy. The advent of the European Grid Infrastructure, combined with the blurring of boundaries between grids, clouds, supercomputing networks and volunteer grids, means that a clear consistent source of information aimed at non-experts is now more important than ever, through dissemination projects such as e-ScienceTalk, that cross national boundaries.

**Objectives**:

* e-ScienceTalk will build on the achievements of the GridTalk project in bringing the success stories of Europe’s e-Infrastructure to policy makers in government and business, to the scientific community and to the general public.
* e-ScienceTalk will work with EGI-InSPIRE and other collaborating projects to expand the scope of the existing GridTalk outputs, and to report on the interactions of grids with e-Infrastructures such as cloud computing and supercomputing.
* The project will explore options for the sustainability of e-ScienceTalk’s products.
* e-ScienceTalk will produce a series of reports aimed at policy makers to disseminate key policy issues underpinning grid and e-Infrastructure development in Europe. The project will also coordinate e-concertation activities.
* The GridCafé, GridCast and GridGuide suite of websites will cover new topics and explore novel web technologies; they will integrate closely with GridPP’s Real Time Monitor, combining live views of grid activity with the human aspects of computing.
* The growing weekly publication, International Science Grid This Week (iSGTW) will bring news and events to the existing and potential e-Science community.
1. EXECUTIVE SUMMARY

This report covers the eleventh quarter of the e-ScienceTalk project, March to May 2013. This document reports on the activities of the eleventh quarter in each work package, summarises any issues raised and previews plans for the final months in PY3. The management report includes summary effort figures, the expected spending profile for the period and includes the project metrics for each work package.

The outputs from WP1 Policy, Impact and Sustainability have been in events, e-ScienceBriefings and GridCasts, producing the final e-ScienceBriefing D1.2.12 which covered the topic of Horizon2020, the next funding framework programme. In Q11, WP2 ran 6 full or mini GridCasts at events in Europe, including the 10th e-Infrastructure Concertation meeting, the International Symposium on Grids and Clouds in Taipei and the EGI Community Forum in Manchester.WP2 also worked on the Real Time Monitor in collaboration with the Science Museum in London. International Science Grid This Week was sent to just over 8770 subscribers by email by WP3, and increased social media followers. An iSGTW promotional poster was produced in collaboration with WP2 for display at the EGI Community Forum 2013 in Manchester and at ISGC’13 in Taipei, along with GridCast posters. WP3 has continued to publish iSGTW, with 13 issues produced during the quarter.

The 10th e-Infrastructure Concertation Meeting, organised in collaboration with the e-ScienceTalk

project, took place at The Hotel in Brussels on 6th and 7th March. The programme for the event aimed to further the EC’s objective to develop a world-class resource as part of a strategy to achieve European leadership in e-Science. The main aim of the meeting was to bring projects together in order to discuss issues related to the completion of the 7th Framework Programme and the start of

an e-infrastructures activity during Horizon 2020 (2014-2020). Over 130 participants attended, and the winners of the FP7 Success Story Competition were announced by the iSGTW Editor at the event in Brussels. The winners were also announced by press release, and stories based on the participant entries will feature in iSGTW in the coming months.

WP1 continues to work on achieving a good balance of information and contributions from collaborating projects in the e-ScienceBriefings. Discussions on the long term support for iSGTW are continuing with Xenomedia and QMUL through the iSGTW Advisory Board.

The project management report confirms that all Deliverables and Milestones have been submitted to the EC on time. An MoU was signed between e-ScienceTalk and iMENTORS, a one-stop-shop data warehouse on all e-infrastructure development projects of Sub-Saharan Africa (SSA). A further agreement between Ubuntunet and iSGTW on shared content is expected, giving e-Sciencetalk enhanced visibility in this region. A no cost project extension to July 31st 2013 was finalised with the EC and the new DoW submitted to NEF. Effort reporting for the eleventh quarter is at 80% of planned effort.

TABLE OF CONTENTS

1 Introduction 6

2 main achievements 7

2.1 Summary 7

2.2 Work packages 7

2.2.1 WP1: Policy, impact and sustainability 7

2.2.2 WP2: GridCafé, GridGuide, GridCast 8

2.2.3 WP3: iSGTW 9

2.3 Issues and mitigation 9

2.3.1 WP1: Policy, impact and sustainability 9

2.3.2 WP2: Gridcafé, GridGuide, Gridcast 9

2.3.3 WP3: iSGTW 10

2.4 Plans for the next quarter 10

2.4.1 WP1: Policy, impact and sustainability 10

2.4.2 WP2: Gridcafé, GridGuide, Gridcast 10

2.4.3 WP3: iSGTW 11

3 Consortium management 12

3.1 Summary 12

3.2 WP4: Management 12

3.2.1 Project management 12

3.2.2 Milestones and Deliverables 12

3.2.3 Consumption of effort 13

3.2.4 Overall financial status 15

3.2.5 WP4: Management issues and mitigation 15

3.2.6 WP4: Plans for the next quarter 16

4 project metrics 17

4.1.1 WP1: Policy, impact and sustainability 17

4.1.2 WP2: Gridcafé, GridGuide, Gridcast 18

4.1.3 WP3: iSGTW 19

4.1.4 WP4: Management 20

5 conclusion 22

6 References 23

# Introduction

This document reports on the activities of the eleventh quarter in each work package for e-ScienceTalk, covering the e-ScienceBriefings, the GridCafé, GridCast and GridGuide, as well as the Real Time Monitor and International Science Grid This Week. The report also summarises any issues raised or addressed during the eleventh quarter, and previews plans for the close of the project. The management report includes summary effort figures for the quarter and includes the project metrics for each work package.

# main achievements

## Summary

This section summarises the main achievements by each work package during the eleventh quarter of the project.

## Work packages

### WP1: Policy, impact and sustainability

E-ScienceTalk launched the final e-ScienceBriefing on Horizon2020 [R1]. This policy document D1.2.12, covered 17 projects and was launched at the 10th e-Concertation Meeting in Brussels in March. The document was also emailed to the EGI dissemination mailing list, as well as the e-IRG Board members.

The e-ScienceTalk team has also attended a number of policy related events during the quarter, including the 10th e-Infrastructure Concertation meeting, the International Symposium on Grids and Clouds in Taipei and the EGI Community Forum in Manchester. A GridCast or mini GridCast was also held at 6 events. At these events and others attended by WP2/WP3, copies of the new e-ScienceBriefings have been distributed.

The 10th e-Infrastructure Concertation Meeting, organised in collaboration with the e-ScienceTalk

project, took place at The Hotel in Brussels on 6th and 7th March. The programme for the event aimed

to further the EC’s objective to develop a world-class resource as part of a strategy to achieve European leadership in e-Science. The main aim of the meeting was to bring projects together in order to discuss issues related to the completion of the 7th Framework Programme and the start of an e-infrastructures activity during Horizon 2020 (2014-2020).

The two day meeting brought together over 130 representatives from the e-Infrastructure landscape, policy makers and funding agencies, and looked at the impact and outcomes from the FP7 funding programme for e-Infrastructures. Sessions covered impact measurement and metrics, a look ahead to the draft programme and timetable for Horizon2020 and a discussion panel on sustainability of e-Infrastructures.

An FP7 Success Story Competition highlighted the best success stories from the FP7 Capacities funding programme in e-Infrastructures in three categories: Excellent Science, Competitive Industries and Better Society. Prizes were awarded to winners and the runners up in each category at the event. Across all the categories, there were 15 entrants to the competition. A jury made up of members of the e-ScienceTalk team, the European Commission and the Editor of iSGTW considered the entrants, and awarded first and second prizes in all three categories. All the entrants of the competition were commended by the jury and will be invited to submit articles to iSGTW based on their success stories.

Delegates commented that the format, content and organisation of the meeting worked well, and it provided an ideal opportunity for networking for the e-Infrastructure community.

A further communications training event took place as part of the programme for the CRISP 2nd Annual Event in Villagen, Switzerland, led by WP1.

### WP2: GridCafé, GridGuide, GridCast

WP2 has worked on e-ScienceTalk’s suite of interactive websites, Gridcafé, GridCast and GridGuide, as well as the main project website and the Real Time Monitor.

During the eleventh quarter, the following work was carried out.

**GridCafé**

* Marketing e-ScienceCity for the final year of the project to boost traffic to the new areas of the site outside GridCaf.
* Completion of a Schools pack from the e-ScienceCity, including an offline version on USB key.
* Gathering feedback on the e-ScienceCity website for the final reports.

**GridCast**

* Small GridCasts took place at the 5th CAPRI Evaluation meeting and the e-IRG meeting.
* Major GridCast for the 10th e-Infrastructure Concertation meeting, the International Symposium on Grids and Clouds in Taipei and the EGI Community Forum in Manchester.
* At the EGI Community Forum, the GridCast team produced 14 videos, uploaded to YouTube. In total, the YouTube videos registered 725 views during the forum week.
* At the EGI Community Forum, the GridCast blog published 24 blog posts. The posts were viewed by 1,330 unique visitors.

**GridGuide**

* WP2 created XSEDE and PRACE site records in the GridGuide, among others, to increase the number of sites in the US and Europe.
* The total of number of sites in GridGuide is 102, meeting the final milestone for GridGuide.
* The new GridPort area is being prepared in e-ScienceCity to include capsule information for each site within the e-ScienceCity template.

**Real Time Monitor**

* The Imperial team worked on display improvements for the RTM for the LHC Collider exhibition at the Science Museum in November 2013.
* Upgraded graphics have been launched due to the WorldWind upgrade.
* The GridCast team displayed the RTM at events attended by e-ScienceTalk, including the EGI Community Forum in Manchester 2013.

### WP3: iSGTW

Weekly issues of iSGTW were produced, 13 in total, including articles, links, images, videos, jobs, events and announcements. The new publication was marketed and promoted at events attended by the e-ScienceTalk team during the quarter, such as the EGI Community Forum in Manchester and the ISGC’13 event in Taipei. Posters were designed in collaboration with WP2, and these were displayed at booths run by EGI and e-ScienceTalk at the EGI Community Forum and at ISGC. The Editor-in-Chief Andrew Purcell reported from the CRISP 2nd Annual event in Villagen, Switzerland.

Overall, the web traffic has increased significantly over this quarter. Page views are now at more than double the same period last year, having reached 161,000 this quarter, an increase of 75% on the previous quarter . Unique visitors are at 55,000, which represents an improvement of 23% on last year. Also, the average duration of visits to the site is up 61% on the same period last year to 02:30 and up 26% on the previous quarter. Bounces are down by 12%, as well. Subscriber numbers have increased to over 8700 due to media partnerships with events. Followers of iSGTW on Twitter now number 1724 with 1152 ‘likes’ on Facebook. Some older stories from the archive are still extremely popular. The top 10 features are mainly old stories. Stefan Janusz’s story, “The mystery of the slowing space probes”, is still very popular with 1,297 page views.

Changes have been made to the iSGTW email and web template at the end of the quarter to slightly reduce the total amount of content each quarter, and to carry event banners for partnership events. Due to the reduced editorial effort at CERN, and to prepare for the Editor role reducing to 0.75FTE after the end of the project, the weekly content has been reduced to 2 articles, a feature and a spotlight article. The first issue with the slightly reduced content was successfully published on 29 May.

## Issues and mitigation

### WP1: Policy, impact and sustainability

One issue foreseen for WP1 is:

* To ensure a good balance of information and contributions from collaborating projects in the e-ScienceBriefings.

WP1 is working to mitigate this issue through developing collaborations and MoUs and by liaising with the policy teams in projects such as EGI-InSPIRE and e-IRG. WP1 is exploring dissemination opportunities with new projects as a result of meetings at the 10th e-Infrastructure Concertation meeting.

### WP2: Gridcafé, GridGuide, Gridcast

For WP2, the following issues have been reported in previous quarters:

* Adding Russian, Chinese and other non-Roman languages to the GridCafé database.
* Displaying jobs from other, non-gLite sources in the RTM.

In order to support adding Russian, Chinese and other non-Roman translations of the GridCafé, separate html sites will continue to be needed, as these are not supported by the content management system.

The RTM is exploring adding additional types of data to the interface including data from the other LHC experiments.

### WP3: iSGTW

In WP3, the following issue has been reported in previous quarters:

* Staffing during the handover with Amber Harmon, as she joins the iSGTW team and gets up to speed.

The editorial team at iSGTW is now fully recruited, with the exception of the 0.5 FTE post at ASGC, which is still being advertised. Due to the reduced editorial effort at CERN, and to prepare for the Editor role reducing to 0.75FTE after the end of the project, the weekly content has been reduced to 2 articles, a feature and a spotlight article.

## Plans for the next quarter

This section outlines for the plans for each work package during the final 2 months of the project.

### WP1: Policy, impact and sustainability

During Q12, a compendium of e-ScienceBriefings will be produced with a foreword by Thierry van der Pyl, Director of DG Communications Networks at the EC. Effort will focus on completing the final deliverables for the project on feedback and metrics, sustainability and impact. Materials from the training sessions will be combined into a final Dissemination Guide for EC projects.

### WP2: Gridcafé, GridGuide, Gridcast

For WP2, a number of developments are planned for the final 2 months.

* **GridCafé**
	+ Marketing e-ScienceCity for the final year of the project to boost traffic to the new areas of the site outside GridCafé.
	+ Creating a Schools pack from the e-ScienceCity, including an offline version on USB key.
	+ Gathering final feedback on the e-ScienceCity website and compiling the final report.
	+ Renewing hosting packages and creating an archive version of the e-ScienceCity site.
* **GridCast**
	+ Small GridCasts are planned for XSEDE’13 in San Diego and ISC’13 in Leipzig.
* **GridGuide**
	+ Transfer capsule content for each site to a new area in e-Sciencecity, called GridPort.
* **RTM**
	+ Carry out modifications to the interface to improve usability and navigation for the LHC Collider exhibition at the Science Museum.

### WP3: iSGTW

For the next quarter, as well as publishing weekly issues of the publication itself, iSGTW will continue to build its Twitter and Facebook following. iSGTW will attend ISC’13 through its media partnership for the event in Leipzig in June 2013 . iSGTW will also aim to increase subscriptions by following up media partnerships with organisers of events outside the existing readership areas, such as for SC’13 in November and the EUDAT 2nd Conference in October . An Advisory Board is planned for July 2013 at the XSEDE’13 event in San Diego.

# Consortium management

## Summary

This section outlines the consortium management activities during the quarter, carried out by WP4 the management work package.

## WP4: Management

### Project management

All Deliverables and Milestones for the quarter have been submitted to the EC on time. An MoU was signed between e-ScienceTalk and iMENTORS, a one-stop-shop data warehouse on all e-infrastructure development projects of Sub-Saharan Africa (SSA). A further agreement between Ubuntunet and iSGTW on shared content is expected, giving e-Sciencetalk enhanced visibility in this region. A no cost project extension to July 31st 2013 was finalised with the EC and the new DoW submitted to NEF. A PMB meeting took place on 8 March 2013 to discuss sustainability for e-ScienceTalk activities.

### Milestones and Deliverables

**Table 1: Quarter 11 Deliverables**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Del. no.**  | **Deliverable name** | **WP no.** | **Nature** | **Due (PM)** | **Delivery date****(PM)** | **Status** |
| D1.2.12 | e-ScienceBriefings  | 1, 2 | R | 32 | 32 | Completed |
| D3.6 | Report on survey of iSGTW readers and annual metrics | 3 | R | 33 | 33 | Completed |

**Table 2: Quarter 11 Milestones**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Milestone number** | **Milestone name** | **WP no.** | **Due (PM)**  | **Delivery date (PM)** | **Status** |
| MS3 | 10th e-Concertation meeting | 1,2,3 | 31 | 31 | Completed |
| MS7 | Posters and marketing materials | 3,2 | 31 | 31 | Completed |
| MS10.11 | PMB meeting | 4 | 31 | 31 | Completed |
| MS4 | GridCasts | 2 | 32 | 32 | Completed |
| MS6 | GridGuide expanded to 100 sites | 2 | 33 | 33 | Completed |

**Table 3: Quarter 12 Deliverables**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Del. no.**  | **Deliverable name** | **WP no.** | **Nature** | **Due (PM)** | **Delivery date****(PM)** | **Status** |
| D1.6 | Briefing final summary | 1,2 | R | 34 |  | In progress |
| D2.4 | Annual upgraded version of the RTM | 2 | O | 34 |  | In progress |
| D2.5 | Final dissemination report on GridCafe, GridGuide and GridCast | 2 | R | 34 |  | In progress |
| D2.6 | Schools pack based on e-ScienceCity | 1,2 | R | 34 |  | In progress |
| D3.7 | Final report on iSGTW marketing | 3 | R | 34 |  | In progress |
| D4.5 | Final report on feedback and metrics | 4 | R | 34 |  | In progress |
| D1.5 | Final report on impact and sustainability | 1 | R | 35 |  | In progress |
| D4.6 | Guide to dissemination for EU projects | 4 | R | 35 |  | In progress |

**Table 4: Quarter 12 Milestones**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Milestone number** | **Milestone name** | **WP no.** | **Due (PM)**  | **Delivery date (PM)** | **Status** |
| MS10.12 | PMB meeting | 4 | 34 |  | In progress |
| MS4 | GridCasts | 4 | 35 |  | In progress |
| MS7 | Posters and marketing materials | 3,2 | 35 |  | In progress |
| MS9 | Increase iSGTW readership by 15% | 3 | 35 |  | In progress |

### Consumption of effort

A summary of the effort consumption by each partner in each work package is included below. Unfunded effort is included where relevant. A summary of the percentage effort delivered in Q11 is included at the end of this section.

#### Overall effort figures per work package

**Table 5: Overall effort achieved in Q11 in PMs (view 1)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package** | **Mar** | **Apr** | **May** | **Total** | **Year plan** | **Linear Q plan** | **Y2 achieved** | **Q11% achieved** | Q10% achieved | Q9 % achieved |
| WP1 | 1.36 | 1.56 | 1.33 | 4.25 | 46 | **4.2** | **92%** | **101%** | 72% | 81% |
| WP2 | 1.39 | 1.28 | 1.92 | 4.59 | 64 | **5.8** | **89%** | **79%** | 62% | 60% |
| WP3 | 1.11 | 1.47 | 1.19 | 3.77 | 52 | **4.7** | **93%** | **80%** | 87% | 141% |
| WP4-M | 0.61 | 0.31 | 0.25 | 1.17 | 17 | **1.5** | **85%** | **78%** | 55% | 120% |
| WP2-UNF | 0.00 | 0.00 | 0.00 | 0 | 8 | **0.7** | **0%** | **0%** | 0% | 0% |
| WP4-UNF | 0.11 | 0.06 | 0.03 | 0.2 | 5 | **0.5** | **39%** | **40%** | 0% | 34% |
| **Total** | **4.58** | **4.68** | **4.72** | **13.98** | **192** | **17.5** | **86%** | **80%** | 66% | 88% |

#### Overall, the effort figures for Q11 are at 80% for the quarter. WP1 reported 101% of effort in the quarter. WP2 reported slightly lower than the planned effort at 79% due to staff illness at Imperial College. WP3 reported 80% of effort, which is supplemented by additional effort from QMUL but is still understrength with regard to staffing. WP4 reported 78% as further effort is expected to be reported to close the project during the extension period.

####

#### Overall effort figures per partner

**Table 6: Overall effort achieved in Q11 in PMs (view 2)**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Partner** | **Mar** | **Apr** | **May** | **Total** | **Year plan** | **Linear Q plan** | **Q11% achieved** | Q10% achieved | Q9 % achieved |
| **CERN** | 0.78 | 1.17 | 1.00 | 2.95 | 67 | **6.1** | **48%** | 65% | 113% |
| **APO** | 0.94 | 1.09 | 1.08 | 3.11 | 34 | **3.1** | **100%** | 55% | 94% |
| **QMUL** | 2.11 | 2.11 | 2.11 | 6.33 | 47 | **4.3** | **147%** | 119% | 77% |
| **IMPERIAL** | 0.14 | 0 | 0.28 | 0.42 | 26 | **2.4** | **18%** | 0% | 21% |
| **EGI.eu** | 0.61 | 0.3 | 0.25 | 1.16 | 18 | **1.6** | **73%** | 52% | 117% |
| **Total** | **4.58** | **4.67** | **4.72** | **13.97** | **192** | **17.5** | **80%** | 66% | 88% |

Q11 represents 27% of the elapsed time of the project. The total overall effort figures for the eleventh quarter are at 80% of planned for the project as a whole. CERN has under reported this quarter, due to reduced staffing levels. QMUL has over reported during PQ11 due to contributions to WP3 and to the final reports. Imperial has significantly under reported this quarter, due to staff illness. EGI.eu has under reported with additional effort expected during the close of the project.

### Overall financial status

The expenditure for the second year of the project is expected to follow the profile outlined below. Financing will be distributed to partners at the end of Year 2 based on the accepted Form C costs, taking into account the 90% ceiling.

**Table 7: Expected expenditure profile PY 3**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Partner** | **WP1** | **WP2** | **WP3** | **WP4** | **Total** | **3rd Year** |
| EGI.eu |  |  |  | 187,694 | 187,694 | 68,252 |
| QMUL | 223,513 | 56,858 | 40,627 |  | 320,998 | 116,727 |
| APO | 28,088 | 154,882 | 28,088 |  | 211,057 | 76,748 |
| Imperial |  | 114,181 |  |  | 114,181 | 41,520 |
| CERN | 69,164 | 77,562 | 319,344 |  | 466,070 | 169,480 |
| **Total** | **320,764** | **403,485** | **388,057** | **187,694** | **1,300,000** | **472,727** |

**Table 8: Estimated Personnel expenditure Q11 (Euros)**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Work package** | **Mar** | **Apr** | **May** | **Cumul Direct** | **Cumul Indirect** | **Cumul Eligible** | **Q11****Estimated****Funding** |
| WP1  | 5,723 | 6,275 | 5,406 | 17,405 | 3,481 | 20,885 | **18,623** |
| WP2  | 6,641 | 6,622 | 9,862 | 23,124 | 4,625 | 27,749 | **24,743** |
| WP3  | 6,708 | 9,095 | 7,470 | 23,273 | 4,655 | 27,928 | **24,903** |
| WP4-M  | 5,063 | 2,678 | 2,316 | 10.056 | 2,011 | 12,068 | **10,760** |
| WP2-UNF  | 0 | 0 | 0 | 0 | 0 | 0 | **N/A** |
| WP4-UNF  | 467 | 233 | 117 | 817 | 163 | 980 | **N/A** |
| **Total**  | **24,602** | **24,904** | **25,170** | **74,675** | **14,935** | **89,610** | **79,029** |

In line with the under spending of the person months planned, the costs of the personnel are lower than the projected estimates. The partners have spent in total 79keuro during the quarter; 129keuros were (linearly) forecast over a 3-month period.

### WP4: Management issues and mitigation

For WP4, a number of issues were monitored in PQ11:

* Identification of funding for the costs of day to day maintenance of the iSGTW website by Xenomedia, once Fermilab funding ceases.

The handover of specific tasks between Xenomedia and QMUL is being co-ordinated by WP4. An upgrade from Drupal 6 to 7 is being explored and will be discussed at the iSGTW Advisory Board meeting at the XSEDE’13 event on 24 July.

### WP4: Plans for the next quarter

The management workpackage will work on the final deliverables for the project, and the ongoing sustainability of the project activities beyond 31 July 2013. A final PMB meeting is planned for 18 June 2013. Future collaborations with projects after the close of e-ScienceTalk are being discussed as a result of meetings at the 10th e-Infrastructure Concertation meeting. As a result, a networking session proposal is being prepared for submission to ICT’13 in Vilnius in November with a consortium of projects including e-ScienceTalk, CHAIN-REDS, Pro-iBIOSPHERE, e4AFRICA and EGI-InSPIRE.

# project metrics

Project metrics have been revised in D4.4 *Annual report on feedback and metrics* [R2]. The revised metrics are now being tracked and are summarised for each work package below. Project level metrics are indicated in bold type.

### WP1: Policy, impact and sustainability

**Table 11: Metrics for Work Package 1**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Metric no.** | **Description** | **Comments** | **Q9** | **Q10** | **Q11** |
| **1.1** | **Projects covered** | **In the e-ScienceBriefings** | **12** | **30 (19+11)** | **17** |
| **1.2** | **Reports and briefings published** | **In print or by email** | **1** | **2** | **1** |
| **1.3** | **Countries where reports or briefings are distributed** | **In print or by email** | **13** | **46** | **10** |
| 1.4 | Policy articles published | In print or online | 2 | 4 | 2 |
| 1.5 | Printed policy reports circulated per briefing | To policy makers | 100 | 200 | 100 |
| 1.6 | Policy events organised | Number organised | 0 | 1 | 0 |
| 1.7 | Attendees at e-ScienceTalk organised policy events | Number of delegates | 0 | 132 | 0 |
| 1.8 | Policy events attended by e-ScienceTalk | Number attended, physically or virtually | 3 | 3 | 2 |
| 1.9 | Delegates at policy events attended by e-ScienceTalk | Number of delegates at events attended. | 500 | 400 | 350 |
| 1.10 | Downloads of policy documents(cumulative) | Measured from the e-ScienceTalk web site | 9128 | 11054 | 13119 |
| 1.11 | Training Sessions/talks delivered | New metric | 2 | 1 | 1 |

### WP2: Gridcafé, GridGuide, Gridcast

**Table 12: Metrics for Work Package 2**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Metric no.** | **Description** | **Comments** | **Q9** | **Q10** | **Q11** |
| **2.1** | **Sites on GridGuide** | **Number of new sites included** | **0** | **10** | **17** |
| **2.2** | **Bloggers contributing to GridCasts** | **Average number of bloggers on GridCast** | **6** | **3 (mini)** | **5** |
| **2.3** | **GridCasts per year** | **Including major and mini GridCasts** | **4** | **5** | **7** |
| **2.4** | **New areas of GridCafé** | **Covering topics other than grid computing** | **0** | **1** | **0** |
| 2.5 | Change in unique visitors to the GridCafé website | From Google Analytics | 3608(+86% from 1935) | 3357(-7%) | 4324(+29%) |
| 2.6 | Ratio of page views to visitors for the GridCafé website | From Google Analytics | 3.13 | 2.79 | 2.58 |
| 2.7 | Number of bloggers for GridCast | Total number of bloggers | 7 | 5 | 8 |
| 2.8 | Blog entries on GridCast | Total number | 44 | 32 | 39 |
| 2.9 | Podcasts on GridCasts | Total number | 7 | 5 | 19 |
| 2.10 | Unique visitors to the GridCast (% new) | From Google Analytics | 75.3 | 82.3 | 76.7 |
| 2.11 | Length of time spent on the GridCast | From Google Analytics | 1:17 | 1:11 | 1:42 |
| 2.12 | EU sites on GridGuide | European based sites |  36 | 45 | 53 |
| 2.13 | Non-EU sites on GridGuide | Non-European located sites | 23 | 26 | 49 |
| 2.14 | Unique visitors to the GridGuide | From Google Analytics | 296 | 114 | 149 |
| 2.15 | Page views of the GridGuide | From Google Analytics | 403 | 157 | 383 |
| 2.16 | GridGuide sites on RTM | Total number | 59 | 59 | 59 |
| 2.17 | Countries in the RTM | Total number[[1]](#footnote-1) | 54 | 54 | 54 |
| 2.18 | Numbers of delegates at events demo-ing the RTM | Including events attended by collaborating projects demo-ing the RTM | 300 | 10400 | 40 |

### WP3: iSGTW

**Table 13: Metrics for Work Package 3**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Metric no.** | **Description** | **Comments** | **Q9** | **Q10** | **Q11** |
| **3.1** | **iSGTW subscribers** | **Registered in the database** | **8249** | **8706** | **8770** |
| **3.2** | **Articles on European projects** | **Based on EU funded projects** | **27** | **18** | **26** |
| **3.3** | **Projects in the iSGTW/GridCafé resources section** | **Total number** | **64 (non added this quarter)** | **64** | **64** |
| **3.4** | **iSGTW printed materials distributed** | **At events attended by e-Science Talk or by collaborating projects** | **Total of 616 (up 6 this quarter)** | **616** | **616** |
| 3.5 | Issues published | Issued to subscribers and posted on the website | 13 | 11 | 13 |
| 3.6 | US articles published | Based on US projects | 44 | 18 | 23 |
| 3.7 | Worldwide articles published | Based on non US or EU projects | 12 | 4 | 8 |
| 3.8 | Unique visitors to the website | From Google Analytics | 43,235 | 54,038 | 54,011 |
| 3.9 | Page views of the website | From Google Analytics | 88,752 | 141,325 | 207,247 |
| 3.10 | Countries visiting the iSGTW website | From Google Analytics | 179 | 176 | 182 |
| 3.11 | Marketing materials distributed | In print or by email or at events | 4 | 5 | 7 |
| 3.12 | Survey responses | Through Zoomerang survey tool | 0 | 113 | 0 |
| 3.13 | Social media subscribers | On Twitter and Facebook | 1394 Twitter + 709 Facebook | 1545 Twitter + 925 Facebook | 1724 Twitter + 1152 Facebook |
| 3.14 | Time spent on the site per visit (minutes) | From Google Analytics | 1:55 | 2:11 | 3:20 |
| 3.15 | Stories shared on social media | Via all social media channels | 495 | 494 | 327 |

### WP4: Management

**Table 14: Metrics for Work Package 4**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Metric no.** | **Description** | **Comments** | **Q9** | **Q10** | **Q11** |
| 4.1 | Deliverables submitted | By email and online | 1 | 3 | 1 |
| 4.2 | Milestones agreed | By email and online | 4 | 3 | 0 |
| 4.3 | Late Deliverable and Milestones | Submitted or agreed after the date agreed with the EC | 0 | 0 | 0 |
| 4.4 | e-ScienceTalk materials produced | Included printed materials, pens, banners etc | 500 pens200 badges | 0 | 300 lanyards |
| 4.5 | Unique visitors to the e-ScienceTalk website | From Google Analytics | 409 | 357 | 447 |
| 4.6 | Referrals from e-ScienceTalk site to other e-ST sites | From Google Analytics | 145 | 115 | 133 |
| 4.7 | Media releases issued | Issued via Alphagalileo and by email | 0 | 0 | 0 |
| 4.8 | Press cuttings | Measured by Google Alerts | 1[[2]](#footnote-2) | 0 | 1[[3]](#footnote-3) |
| 4.9 | Events attended | By e-ScienceTalk project team | 6 | 3 | 6 |
| 4.10 | Social media subscribers | On Twitter | 2059 | 2143 | 2217 |
| 4.11 | Media partnerships at events | Number of events with e-ScienceTalk as media partners | 3 | 1 | 3 |
| 4.12 | Number of MoUs signed | With collaborating projects | 0 | 1 | 1 |

# conclusion

The eleventh quarter for e-ScienceTalk has seen a range of outreach activities and launches. Expenditure of costs and effort are slightly below planned for the quarter. All Deliverables and Milestones have been completed and submitted on time during the quarter.

# References

|  |  |
| --- | --- |
| R1 | D1.2.12 e-ScienceBriefing<https://documents.egi.eu/document/1747> |
| R2 | D4.4 Annual Report on Feedback and Metrics <https://documents.egi.eu/document/1328>  |

1. <http://gridportal-ws01.hep.ph.ic.ac.uk/dynamic_information/egee-locations.xml> [↑](#footnote-ref-1)
2. <http://www.zive.cz/clanky/osm-zivych-map-ktere-vam-popisou-co-se-deje-ve-svete/sc-3-a-166010/default.aspx> (Czech technology news site featured RTM) [↑](#footnote-ref-2)
3. http://www.scienceworldreport.com/articles/7661/20130620/coordinated-approach-science-europe.htm [↑](#footnote-ref-3)