Consumption of resources overview	2

Explanation of the use of the resources	4

1.	PARTNER short name EGI.eu	5

2.	PARTNER short name QMUL	6

3.	PARTNER short name APO	7

4.	PARTNER short name Imperial	8

5.	PARTNER short name CERN	9

Form C and Summary financial report (draft version 30-08-2013)	10

Report on the distribution of the grant before acceptance of PY3 costs and EC final payment	11

05/09/2013

This version includes revisions:

- Imperial costs revised on 5/09/13 (+11,058€)

- adjustment of EGI.eu funding claimed (-291€)

- CERN adjustments made in PY2 (--118€)

# Consumption of resources overview

| Table 1: Overall effort achieved in YEAR3 (view 1) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package | Total | Project plan | Linear Y3 plan | YEAR 3 % achieved |  |  |  |  |
| WP1 | 15.5 | 46 | 16.7 | 93% |  |  |  |  |
| WP2 | 18.7 | 64 | 23.3 | 80% |  |  |  |  |
| WP3 | 17.5 | 52 | 18.9 | 92% |  |  |  |  |
| WP4-M | 5.1 | 17 | 6.2 | 82% |  |  |  |  |
| WP2-UNF | 0.0 | 8 | 2.9 | 0% |  |  |  |  |
| WP4-UNF | 0.6 | 5 | 1.8 | 31% |  |  |  |  |
| Total | 57.3 | 192.0 | 69.8 | 82% |  |  |  |  |
| Table 2: Overall effort achieved in YEAR3 (view 2) |  |  |  |  |  |  |  |  |
| Partner | Total | Year plan | Linear Y3 plan | YEAR 3 % achieved |  |  |  |  |
| CERN | 15.6 | 67 | 24.4 | 64% |  |  |  |  |
| APO | 10.7 | 34 | 12.4 | 86% |  |  |  |  |
| QMUL | 20.9 | 47 | 17.1 | 122% |  |  |  |  |
| IMPERIAL | 5.0 | 26 | 9.5 | 53% |  |  |  |  |
| EGI.eu | 5.2 | 18 | 6.5 | 79% |  |  |  |  |
| Total | 57.3 | 192.0 | 69.8 | 82% |  |  |  |  |

There are few deviations (1-2%) of the PMs declared through EGI.eu portal for the purpose of the quarterly reports, against the PMs declared in the Justification of resource. This is due either to the nr of annual hours used by EGI.eu system to convert the days declared by the partners into PMs and/or because some hours have been omitted into EGI.eu portal at the time of the preparation of the quarterly reports.

Table 3: Actual Estimated expenditure PY3 (based on From C recorded in NEF)

|  | Funding planned Y3 | Costs claimed Direct | Costs claimed Indirect | Costs claimed Eligible | Funding requested (2) | Used Y3 % |
| --- | --- | --- | --- | --- | --- | --- |
| EGI.eu | 92,212 | 77,687 | 15,237 | 92,924 | 82,243 | 89% |
| QMUL | 130,548 | 101,088 | 19,034 | 120,122 | 107,201 | 82% |
| APO | 78,344 | 61,723 | 12,344 | 74,067 | 63,921 | 82% |
| Imperial | 46,089 | 39,122 | 23,473 | 62,595 | 41,860 | 91% |
| CERN (1) | 105,725 | 117,015 | 68,508 | 185,523 | 125,008 | 118% |
|  | 452,918 | 396,635 | 138,596 | 535,231 | 420,233 | 93% |

- includes -118 adjustments on PY2

- excludes costs of participation to the review (Sept 12-13)

Table 4: Project Total Expenditure

Based on From C recorded in NEF and on accepted funding in RP1 and RP2 and funding claimed in RP3

|  | Total Funding Amendment N2 | Used Y1 | Used Y2 | Funding requested Y3 | Used Total Funding % |
| --- | --- | --- | --- | --- | --- |
| EGI.eu | 230,494 | 66,167 | 72,115 | 82,243 | 96% |
| QMUL | 285,688 | 64,185 | 90,955 | 107,201 | 92% |
| APO | 211,057 | 71,887 | 60,826 | 63,921 | 93% |
| Imperial | 108,831 | 27,492 | 35,250 | 41,860 | 96% |
| CERN | 463,930 | 249,763 | 108,442 | 125,008 | 104% |
|  | 1,300,000 | 479,494 | 367,588 | 420,233 | 97% |

The costs recorded in NEF are subject to change after the audit in preparation for CERN and EGI.eu. In addition partners will submit a final version of the costs including the travel costs incurred for the participation in the final EC review 12-13 September.

# Explanation of the use of the resources

The following tables summarize the explanation of personnel costs, subcontracting and any major costs incurred by each beneficiary, such as the purchase of important equipment, travel costs, large consumable items, etc., linking them to work packages.

The partners QMUL, Imperial and CERN use the ‘Special transitional flat rate’ Cost model at 60%. However the initial tables into NEF record a flat rate @ 20%.

## PARTNER short name	EGI.eu

Table 3.1 Personnel, subcontracting and other major cost items for the period

| Work Package | Item description | Amount in € | Explanations |
| --- | --- | --- | --- |
| WP1 - Grid policy | Personnel effort |  |  |
| WP2 - GridCafe |  |  |  |
| WP3 - iSGTW |  |  |  |
| WP4- Mgmt |  | 52,366 € | C Gater-Newhouse Coordinator: 4.33PMs; C Bitoune Project Finance Assistant: 1.42 PMs;S Andreozzi and C Asero Policy team: 0.22 PMs Unfunded PMs for S Newhouse: 0.06 |
|  | Subcontracting | 1,500 € | Freelancer writing for iSGTW articles |
| WP1 - Grid policy | Travel costs |  |  |
| WP2 - GridCafe |  |  |  |
| WP3 - iSGTW |  |  |  |
| WP4- Mgmt |  | 5,296 € | 2012: EUDAT 21-24 Oct Barcelona; EC review 14-15 Oct Brussels; e-Challenge 16-19 Oct Lisbon PT 2013: TNC 3-6 June Maastricht, NL; CAPRI 17-18 Apr 2013, Utrecht, NL; XSEDE 20-25 July 2013 USA; C. Asero and S Andreozzi: e-infra Concertation meeting 6-7 March 2013 in Brussels |
|  | e-Concertation Meeting | 16,086 € | Organisation of 10th e-Concertation 6-14 March 2013 in Brussels |
|  | Remaining direct costs | 2,439 € | 2012-2013 OC: subscription, publications articles, printing slides, bank costs |
|  | Indirect costs | 15,237 € | flat rate @ 20% or 60%. No overhead applies on subcontracting costs |
| TOTAL COSTS |  | 92,924 € |  |

Situation of eligible budget and PM plan: 6.03 PMs used in Y3

Audit in preparation

## PARTNER short name	QMUL

Table 3.1 Personnel, subcontracting and other major cost items for the period

| Work Package | Item description | Amount in € | Explanations |
| --- | --- | --- | --- |
| ALL | Personnel direct costs | 82,709 € |  |
| WP1 - Grid policy | Personnel effort |  | Personnel Zara Qadir 6.30 person months WP1 Personnel Stefan Janusz 6.85 man months WP1 |
| WP2 - GridCafe |  |  | Personnel Zara Qadir 3.30 person months WP2 Personnel Stefan Janusz 1.85 man month WP2 |
| WP3 - iSGTW |  |  | Personnel Stefan Janusz 2.84 man months WP3 |
| WP4- Mgmt |  |  |  |
|  | Subcontracting | 0 | n/a |
| WP1 - Grid policy | Travel costs | 11,331 € | Z Qadir (ZQ) & S Janusz (SJ), S Lloyd (SL) EUDAT, Barcelona 22-24/10/12; ZQ & SJ to EGI Technical Forum, Prague 17-21/9/12; ZQ to eChallenges, Lisbon 16-19/1012; SJ Project presented to Brussels 14-15/10/12; SJ E-Science Talk, CERN, Geneva 27-28/11/12; ZQ & SJ to eConcertation, Brussels 6-7/3/13; ZQ to ISGC 2013, Taipei16-22/3/13; ZQ & SJ EGI Community Forum, Manchester, 25/2/13; e-IRG Workshop, Dublin 22-25/5/13; ZQ&SJ Science Communication Conference, London 16-17/5/13; ZQ & SJ EGI 2013 Conference Manchester 8-12/4/13 |
| WP2 - GridCafe |  |  |  |
| WP3 - iSGTW |  |  |  |
| WP4- Mgmt |  |  |  |
|  | Equipment | 0 | n/a |
|  | Remaining direct costs | 6,148 € | consumables |
|  | Indirect costs | 19,934 € | STFC; No overhead applies on subcontracting costs |
| TOTAL COSTS |  | 120,122 € |  |

Situation of eligible budget and PM plan: 21.14 PMs used in Year 3

Draft version dated 28-08-2013

## PARTNER short name	APO

Table 3.1 Personnel, subcontracting and other major cost items for the period

| Work Package | Item description | Amount in € | Explanations |
| --- | --- | --- | --- |
| WP1 - Grid policy | Personnel effort | 5,749 € | 1.36 PM Andre-Pierre Olivier |
| WP2 - GridCafe |  | 39,221 € | 7,45 PMs; Andre-Pierre Olivier 0.64 and Corentin Chevalier 6.81 |
| WP3 - iSGTW |  | 6,581 € | 1.4 PMs: Andre-Pierre Olivier 0.75; Corentin Chevalier 0.64 |
| WP4- Mgmt |  | 1,983 € | Unfunded 0.5 PMs Andre-Pierre |
|  | Subcontracting | 0 € | n/a |
| WP1 - Grid policy | Travel costs |  | n/a |
| WP2 - GridCafe |  | 5,775 € | list date and place of Travels related to the project activities |
| WP3 - iSGTW |  |  | n/a |
| WP4- Mgmt |  |  | n/a |
|  | Equipment | 0 € | n/a |
|  | Remaining direct costs | 2,414 € | Web and virtual world;images 3D |
|  | Indirect costs | 12,344 € | 20%. No overhead applies on subcontracting costs |
| TOTAL COSTS |  | 74,067 € |  |

Situation of eligible budget and PM plan: 10.7 used in Year 3

Final version dated 30-08-2013

## PARTNER short name	Imperial

Table 3.1 Personnel, subcontracting and other major cost items for the period

| Work Package | Item description | Amount in € | Explanations |
| --- | --- | --- | --- |
| WP1 - Grid policy | Personnel effort |  |  |
| WP2 - GridCafe |  | 36,351 € | Dr. Janusz Martyniak; Total months for the period = 5.5 |
| WP3 - iSGTW |  |  |  |
| WP4- Mgmt |  |  |  |
|  | Subcontracting | 0 | n/a |
| WP1 - Grid policy | Travel costs |  | n/a |
| WP2 - GridCafe |  | 2,771 € | EGI Technical Forum - Prague - September '12; e-ScienceTalk meeting - CERN - November '12; e-ScienceTalk review meeting - Brussels - October '12; e-ScienceTalk review meeting - Brussels - October '12; Dr. D. Colling & Dr. J. Martyniak - Travel to final review meeting 12-13 Sept 13 |
| WP3 - iSGTW |  |  | n/a |
| WP4- Mgmt |  |  | n/a |
|  | Equipment | 0 | n/a |
|  | Remaining direct costs | 0 | n/a |
|  | Indirect costs | 23,473 € | STFC; No overhead applies on subcontracting costs |
| TOTAL COSTS |  | 62,595 € |  |

- Situation of eligible budget and PM plan: 5.5 PMs used in Year 3

Draft version dated 23-08-2013

## PARTNER short name	CERN

Table 3.1 Personnel, subcontracting and other major cost items for the period

| Work Package | Item description | Amount in € | Explanations |
| --- | --- | --- | --- |
| WP1 - Grid policy | Personnel direct costs | 12,973 € | 1.83 PM - Fellow |
| WP2 - GridCafe |  | 7.010 € | 1.05 PM - Fellow |
| WP3 - iSGTW |  | 85,664 € | 13.12 PM - Fellow |
| WP4- Mgmt |  |  |  |
|  | Subcontracting | 1,137 € | Audit costs |
| WP1 - Grid policy | Travel costs | 787 € | 2 person travelling to: eScience talk review Brussels 15/10/2012 |
| WP2 - GridCafe |  | 664 € | 1 person travelling to: 10th e-Infrastructure Concertation meeting Brussels 06/03 - 07/03/2013 |
| WP3 - iSGTW |  | 8,780 € | 2 persons travelling to: EGI Technical Forum Prague 17/09 - 21/09/2012 / 1 person traveling to: ISC Cloud '12 Frankfurt 23/09 - 25/09/2012 / 1 person travelling to: SC12 Salt Lake City 9/11 - 17/11/2012 / 1 person travelling to: EMI Community Forum Manchester 2013 08/04 - 12/04/2013 / 1 person travelling to: ISC 13 & Prace Scientific Conference Leipzig 16/06 - 20/06/2013 / 1 person travelling to: CRISP annual meeting Villigen 18/03/2013 - 19/03/2013 |
| WP4- Mgmt |  |  | n/a |
|  | Equipment | 0 | n/a |
|  | Remaining direct costs | 0 | n/a |
|  | Indirect costs | 69,527 € | 60%. No overhead applies on subcontracting costs |
| TOTAL COSTS[1] |  | 186,541 |  |

Summary explanation if major deviation cost budget and from person-month budget

- Situation of eligible budget and PM plan: Total PMs 16 used in Year 3

Audit in preparation

# Form C and Summary financial report (draft version 06-09-2013)

The participants FORM C, from each beneficiary and from each third party are submitted via the NEF portal. The summary financial report is accessible on the portal. The current session is not submitted. Partners participating to the review on 12-13 September will claim their travel costs and then submit their Financial Statement for PY3. Partners EGI.eu and CERN are currently audited and will submit once their costs are cleared by the auditor.

This version includes Imperial costs revised on 5/09/13.

# Report on the distribution of the grant before acceptance of PY3 costs and EC final payment