## Slide 1: EGI-InSPIRE QR15 - Summary
Tiziana Ferrari
EGI-InSPIRE Project Director, EGI.eu
tiziana.ferrari@egi.eu

## Slide 2: NA1: Management
Revision of PY4 DoW as of Jan 2014 to take into account reviewer’s comments
  Strengthening of policy, business and strategic activities
  User engagement
8 PM PY5 extension and planning of PY5 activities to ensure continuation of strategic work
Finalization of EGI core activity bids
Handover of NA1 Project Management to Y. Legre/EGI.eu director as of Feb 01 2014
Handling of breach of obligations under the Consortium Agreement by the German JRU

## Slide 3: NA2: Communications
Active in organising EGI Community Forum 2014
Attended external meetings
  ICT2013: 5,000 attendees
  SuperComputing 2013: 10,000 attendees
Prepared for EGI presence at 4 scientific meetings
  ICT2013 in Vilnius
  Supercomputing’13 in Denver
Collaborated with UCST to upload 1 webinar hosted by EGI.eu
Outreach Officer and Graphic Designer roles filled
Published 14 news items, 2 case studies and the “Inspired” newsletter.
6 articles referencing or focusing on EGI published in various media, including an editorial in Pan European networks’ Science and Technology magazine ç
Notes: States 4 meetings, but only 2 are listed – since the list are the same, maybe should combine and expand activity
What issue of the inspired newsletter?
6 articles – use a subbullet to summarize topics

## Slide 4: NA2: Strategy and Policy
MoU: Signed with APARSEN and Helix Nebula Marketplace
PY5: Developed new work package to describe activities until Dec 2014 including strategy, policy, and business models
Pay for Use Proof of Concept: Drafted work plan and timeline
Completed selection and hiring of Business Development Expert
EGI Solutions White paper: Drafted structure and content for 4 solutions (merged two)
EGI Towards H2020: Contributed to the organisation and session on cloud and business models
EGICF14: Contribution to program committee, organisation of 3 workshops

## Slide 5: NA2: Strategy and Policy
EUGridPMA/IGTF: Preparing new policies in the area of differentiated identify assurance levels, trusted credential stores and scalable management of user credentials; advanced draft of Identifier-Only Trust Assurance (IOTA) profile
SPG: Revised AUP to align with new EGI Federated Cloud services and raised importance of operational security
Security for Collaborating Infrastructures: Progress in common standard trust framework across e-Infrastructures

## Slide 6: NA2: Technical Outreach to New Communities (EGI.eu)
Publication of the EGI Engagement Strategy: http://go.egi.eu/engagementstrategy
Progress with the execution of existing Engagement projects:
  ELIXIR VT – formally closed, technical collaboration with ELIXIR began (cloud-based setups)
  Technology Study for CTA VT – formally closed, MoU and portal setup with SCI-BUS in PQ16
  Towards a Chemistry, Molecular & Materials Science and Technology VRC VT – First steps towards a VRC portal taken with SCI-BUS, XSEDE. MoU and VRC plan to be finalised in PQ16.
  ENVRI Study Case with EISCAT_3D - implementation of a proof of concept system for a 2TB historical dataset based on the EGI Federated Cloud and OSGC.
  EGI-DRIHM collaboration – upgade to gUSE 3.6.1 and successful submission of jobs to EGI
  9 Federated Cloud use cases
Progress with the scoping of new Engagement projects:
  During a F2F meeting with ELIXIR two technical pilots have been scoped using technologies from the EGI Federated Cloud.
  NGI-ESFRI and NGI-Community engagement tables show active links between the NGIs and ESFRIs, and scientific communities. These will be used in February to scope new VTs: https://documents.egi.eu/document/2073; https://documents.egi.eu/document/2074
  A series of meetings between the developers and providers of the DIRAC ‘interware’ system and various scientific communities.
Notes:     9 Federated Cloud use cases – what did you do?

## Slide 7: NA2: Technical Outreach to New Communities (Global tasks)
AppDB: http://appdb.egi.eu
  Extension of the Virtual Appliance Marketplace based on feedback of early adopters through the EGI Federated Cloud.
    Service is available at https://appdb-dev.marie.hellasgrid.gr/
    Documented: https://wiki.egi.eu/wiki/Fedcloud-tf:WorkGroups:Scenario8:AppDB-VA-Marketplace
  EGI Scientific Discipline API: https://rt.egi.eu/rt/Ticket/Display.html?id=6245
  Training session submission to EGI CF2014: Image lifecycle management on the EGI Federated Cloud
Customer Relationship Management system (CRM): http://crm.egi.eu
  Extension of the CRM based on feedback of early adopters: Improved search, home page
Training Marketplace: http://training.egi.eu
  Upgrade to Drupal 7; Improved Tag cloud
  Hardening the testing and development systems with VMs
  Campaigning for national funding to build a sustainable Training Marketplace for the future, gathering user feedback and requirements for such a system
  Test system to deploy marketplace for other customers (besides EGI). To be released for other customers soon.

## Slide 8: SA1: Operations
Collaborations with OSG and XSEDE to enable COMPCHEM
Collaboration with EUDAT to enable EISCAT 3D community to benefit from both projects
Collaboration with BioVel project to provide monitoring infrastructure
Extension of the accounting infrastructure
  QCG, Globus, ARC, Unicore middlewares publishing campaign
  combined MPI and non-MPI accounting, Cloud, Storage, and Application accounting
  Pay for Use accounting, a test group of sites are now publishing a cost in EUR per HEPSPEC6 hour
Migration to SHA-2 compatible software
Migration to UMD3 compatible software

## Slide 9: SA1: Operations
GLUE correctness monitoring
Call for resources for Resource Allocation activity has been launched
Decision to increase Resource Centre availability and reliability threshold from 70%/75% to 80%/85%
Plan for integration of the EGI Cloud Infrastructure with the grid production infrastructure
Review of Operation Level Agreements framework and related SLAs with help from FedSM project

## Slide 10: SA4: Mini-Projects
Good collaboration with target domain continues
  Mini project management effort drops to a minimum
Tangible results
  The MOOC was held during the last quarter
  The rOCCI solution was partially released for production
    Remaining components will follow next quarter
  A production release of Stoxy implementing the CDMI interface is expected for the final mini-project quarter
  The OCCI connector for Slipstream v2 will be available in production in PQ16
  A cloud-init based VM contextualisation solution including Web UI will be available in PQ16
  A set of Cloud best practices have been published, and will be complemented with an extended set of design patterns
  The VO administration portal is now deployed in production for the biomed VO, and others (e.g. Shiwa portal VO) are already queuing up for service
  The alternative A/R computing service will be deployed to production at the end of the mini-project
  Version 1 of the e-Grant tool for central resource allocation is now in production
Notes: MOOC was held – what do you mean by “was held”?
Several “tangible results” are stated to be ready for the next PQ – would expect to read what was done, then in ( ) ready for next quarter
Or split what was done and what will be done in separate headings

## Slide 11: JRA1: Operational Tools
Operations Portal
  Concentrated effort on refactoring the portal - started in QR13.
    v3.0 will include the refactoring work - will be deployed in pre-production in February and in production in March.
    New features to satisfy EGI CSIRT requirements
    New page summarizing the list of VO security contacts
    Broadcast to VO security contacts
GOCDB
  GOCDBv5.1: released on the 26 November 2013
    Various RT satisfied
  GOCDBv5.2: in testing (in production by February 2014):
    Extensibility mechanism (fundamental to realize the Pay-for-Use PoC)

## Slide 12: JRA1: Operational Tools
EGI Helpdesk (GGUS)
  During PQ15, two major releases has been delivered, the release note are available at https://ggus.eu/pages/owl.php.
SAM
  Work started on SAM v. 22.1 with primary aim to fix various issues identified during the deployment of SAM v. 22
  Significant progress was made in the support of the migration of SAM central services to consortium CNRS, SRCE and GRNET
Accounting Repository
  New release of Apel and SSM software with bug fixes
  Accounting for new resources types:
    New sites added for cloud and storage
  Pay-for-Use:
    A group of sites are now publishing a cost in Euros per HEPSPEC06 hour exploiting the new GOCDB extensibility mechanism

## Slide 13: JRA1: Operational Tools
Accounting Portal
  Security work
  Regionalization on testing in NGI_GR
  Monetary cost computation for all views, backend implementation
  Further Core refactoring
  OOP migration
  MPI Storage and backend implementation finalized
  Storage accounting first implementation
  Country and NGI support for storage accounting
  Revised codebase for new accounting.
  Work on summary view
Metrics Portal
  Fixed cosmetic bugs on chrome
  Changes in quarterly views and Excel reports.
  Changes for QR15
  CSS Improvements

## Slide 14: JRA1: Operational Tools (Meetings)
EGI towards Horizon 2020 Workshop:
  https://indico.egi.eu/indico/conferenceDisplay.py?confId=1893
GGUS advisory board meetings
  http://indico.egi.eu/indico/categoryDisplay.py?categId=78