# 1st Meeting of the EGI-ELIXIR Pilot

Integrating ELIXIR reference datasets within the European Grid Infrastructure

Date: Thu 20 Nov 2014 (20/11/2014) 11:00 CET – Skype Teleconference

# Participants

| Name | Affiliation | Country |
| --- | --- | --- |
| Fotis E. Psomopoulos | AUTH | GR |
| Gergely Sipos | EGI.eu | NL |
| Nuno Ferreira | EGI.eu | NL |
| Diego Scardaci | EGI.eu | NL |
| Giacinto Donvito | INFN Bari | IT |
| Afonso Duarte | ITQB | PT |
| Marios Chatziangelou | IASA | GR |
| William Karageorgos | IASA | GR |

# Agenda

- kick-off meeting of the EGI-ELIXIR Pilot

- Review of the 6 Tasks with the respective Task Leaders

# Minutes

GS: Quick overview of the pilot proposal

All: Review of each Task by the respective Task Leader using the corresponding Google Sheet.

General Actions:

- Officially involve ELIXIR in the Pilot (connect with Rafael C. Jimenez)

- Contact ELIXIR Liaison Nicola Kay regarding the original Google Doc proposal

  - Required affiliation with ELIXIR-GR as named?

  - Current status of the Pilot as an ELIXIR affiliated pilot?

- Setup a dedicated general mailing list and a wiki page (instead of the Google Doc)

  - Send a welcome email to all involved parties

- Investigate: add pilot within the ELIXIR proposal to EINFRA (coordinated by Tommy @ CSC).

  - Link to scientific activities

  - Produce a short text for Giacinto regarding the particular relevant use-cases

- Define “Dataset”, “Data Source” and “Database”, providing also relevant examples and use-cases

- Task 1 & 2: Connect to EBI regarding existing dataset (ELIXIR network)

- Task 4: Get meta-info on existing tools for data replication

- Task 2 & 5: Produce a questionnaire regarding both data and tools employed.

  - Should be send out late 2014 / early 2015

- Task 6 should start after Task 3

- Setup a monthly teleconference for all Task Leaders, but open to all interested parties

Next teleconference: Thu 11 Dec 2014 (11/12/2014) 11:00 CET – Skype Teleconference