1st Meeting of the EGI-ELIXIR Pilot

Integrating ELIXIR reference datasets within the European Grid Infrastructure

**Date**: Thu 20 Nov 2014 (20/11/2014) 11:00 CET – Skype Teleconference

# Participants

|  |  |  |
| --- | --- | --- |
| **Name** | **Affiliation** | **Country** |
| Fotis E. Psomopoulos | AUTH | GR |
| Gergely Sipos | EGI.eu | NL |
| Nuno Ferreira | EGI.eu | NL |
| Diego Scardaci | EGI.eu | NL |
| Giacinto Donvito | INFN Bari | IT |
| Afonso Duarte | ITQB | PT |
| Marios Chatziangelou | IASA | GR |
| William Karageorgos | IASA | GR |

# Agenda

* kick-off meeting of the EGI-ELIXIR Pilot
* Review of the 6 Tasks with the respective Task Leaders

# Minutes

GS: Quick overview of the pilot proposal

All: Review of each Task by the respective Task Leader using the corresponding [Google Sheet](https://docs.google.com/spreadsheets/d/1gcSNCNBdwIgNN8URrj0b2w4WT18VA04BHOi5csT0HGM/edit#gid=1080851537).

**General Actions**:

* Officially involve ELIXIR in the Pilot (connect with Rafael C. Jimenez)
* Contact ELIXIR Liaison Nicola Kay regarding the original Google Doc proposal
	+ Required affiliation with ELIXIR-GR as named?
	+ Current status of the Pilot as an ELIXIR affiliated pilot?
* Setup a dedicated general mailing list and a wiki page (instead of the Google Doc)
	+ Send a welcome email to all involved parties
* Investigate: add pilot within the ELIXIR proposal to EINFRA (coordinated by Tommy @ CSC).
	+ Link to scientific activities
	+ Produce a short text for Giacinto regarding the particular relevant use-cases
* Define “Dataset”, “Data Source” and “Database”, providing also relevant examples and use-cases
* Task 1 & 2: Connect to EBI regarding existing dataset (ELIXIR network)
* Task 4: Get meta-info on existing tools for data replication
* Task 2 & 5: Produce a questionnaire regarding both data and tools employed.
	+ Should be send out late 2014 / early 2015
* Task 6 should start after Task 3
* Setup a monthly teleconference for all Task Leaders, but open to all interested parties

*Next teleconference*: Thu 11 Dec 2014 (11/12/2014) 11:00 CET – Skype Teleconference