# 2nd Meeting of the EGI-ELIXIR Pilot

Integrating ELIXIR reference datasets within the European Grid Infrastructure

Date: Thu 11 Dec 2014 (11/12/2014) 11:00 CET – Skype Teleconference

# Participants

| Name | Affiliation | Country |
| --- | --- | --- |
| Fotis E. Psomopoulos | AUTH | GR |
| Gergely Sipos | EGI.eu | NL |
| Nuno Ferreira | EGI.eu | NL |
| Giacinto Donvito | INFN Bari | IT |
| Afonso Duarte | ITQB | PT |
| Marios Chatziangelou | IASA | GR |
| William Karageorgos | IASA | GR |

# Agenda

- Review of the agreed actions

- Progress report on the six Tasks

# Minutes

FP: Quick overview of the actions taken after the 1st meeting

- Mailing List, Wiki Page and DocDB have been setup by Nuno

- First contact with N. Kay (ELIXIR)

AD: Joao Pina to be included in the Pilot as part of the ELIXIR-PT node

- Already included in mailing list

- participation to the Pilot

GS: Has the pilot been accepted as an Officially recognized ELIXIR Pilot

- Question to Nicola Kay

  - Already two Nodes are involved in the Pilot: INFN (ELIXIR-IT) and ELIXIR-SI

  - Should we aim for endorsement from existing ELIXIR Nodes? If yes, are there any constraints regarding status (full member vs observers)?

Task 1: In progress

Task 2: Initial questionnaire has been setup in SurveyMonkey

- Migrate to LimeSurvey within EGI

- Circulate final questionnaire after the Winter Holiday (i.e. January 2015)

Task 3: WK provided first Schema of the Meta-Data (link)

- Review the information in the Google Sheet for similar schemas for sharing datasets

- Upload the provided Schema to DocDB

Task 4: Ongoing discussion with the ELIXIR Task Force (EGI Webinar)

Task 5: In progress

Task 6: In progress

General Actions:

- Make contact with the BioMedBridges conference 15-19/12

  - Send WikiPage URL

- Provide information to Sara Coelho for EGI Newsletter article on Pilot

Next teleconference: Setup a doodle open for everyone for week 12-16/01/2015

# Useful Links

Pilot Wiki Page: https://wiki.egi.eu/wiki/Integrating_Reference_Datasets

Dedicated DocDB: https://documents.egi.eu/public/ShowDocument?docid=2361

Pilot Mailing List: https://mailman.egi.eu/mailman/listinfo/elixir-pilot

Resources Google Sheet: Google Sheet