EGI-Engage

# Deliverable/Milestone review form

| Details of the document being reviewed |  |  |  |
| --- | --- | --- | --- |
| Title: | Production portal for EISCAT_3D | Document identifier: | EGI-doc-2663 |
| Project: | EGI-Engage | Document url: | https://documents.egi.eu/document/2663 |
| Author(s): | Ingemar Häggström, Gergely Sipos | Date: | 26/2/16 |

| Identification of the reviewer |  |  |  |
| --- | --- | --- | --- |
| Reviewer: | Kostas Koumantaros | Activity: | PMB |

# General comments on the content

Comments from Reviewer:

Even though this document is well written, it seems to be a bit out of scope with plenty information about EISCAT_3D and not the portal itself. Also by reading the document one should be able to answer the following questions - In Section 3 Roadmap: Why does does the Portal Specification task took so long and what is the outcome - In Section 4 1st Portal Version: Why was dirac chosen as a baseline ? How does it replaces the OpenSearch GeoSpatial Catalogue. Minor corrections can be found in the attached document.

Response from Author:

The corrections from the attached document have been incorporated into the new version. Concerning the three comments above: - The first stage took this long because the following activities were performed – This has been added into the milestone (Section 3): - Understand impact of ESA decision on CC workplan - Redefine new timetable and re-negotiating CC members’ role - Establish partnership with E3DS and EUDAT projects - Identify suitable portal technology - Define goals, architecture and capabilities of first portal implementation - Output: D6.3 deliverable, 29 Feb Effort consumption during this period was not as much as with the originally foreseen roadmap. - DIRAC has a component, called ‘File and Metadata Catalog’ (DIRAC File Catalogue – DFC in short). This component provides logical name space for registration and description of data (files) together with the information of the location of physical copies. DFC is a central service to build eventual distributed data management systems which are exposed to the users in a form of a distributed file system. This is now described with more details in Section 4. The CTA community is using DIRAC also as a file catalogue and as a job scheduler to run (1) file transformation jobs on a regular basis and (2) user jobs on-demand. A presentation about this is available at https://indico.egi.eu/indico/contributionDisplay.py?contribId=9&confId=2544.

Additional comments

(not affecting the document content e.g.  recommendations for the future)

From reviewer:

# Detailed comments on the content

| N° | Page | § | Observations | Reply from author (correction / reject, …) |
| --- | --- | --- | --- | --- |

# English and other corrections:

Note: English and typo corrections can be made directly in the document as comments.