EGI-InSPIRE

Annual Report on the status of EGI’s User Services and Community Coordination

EU DELIVERABLE: D3.2

| Document identifier: | EGI-doc-386, version 2 |
| --- | --- |
| Date: | 11/03/2011 |
| Activity: | NA3 |
| Lead Partner: | EGI.eu |
| Document Status: | DRAFT |
| Dissemination Level: | PUBLIC |
| Document Link: | https://documents.egi.eu/document/386 |

Abstract The first year of the EGI-InSPIRE project has seen the establishment of the User Community Support Team at the EGI.eu headquarters in Amsterdam and through this team, the user and community support functions have been robustly defined. The team’s role within the broad context of the European Grid Infrastructure (EGI) has been to harness the efforts and needs of traditional and emerging new communities, thereby creating a collaborative environment where efforts are pooled to the clear benefit of scientific researchers across Europe. Strong working relationships have been cultivated with the National Grid Initiative (NGI) Support Teams as well as with emerging Virtual Research Communities (VRC) whereby we can communicate and support communities of researchers with common interests and practices. The biggest challenge has been the lack of funded projects to help coalesce the domain-specific user communities which has led to weaker than expected sustainability plans emerging from some of these Heavy User Communities. For Year 2 of the project, three key areas of work have been planned. Firstly, even stronger communication between the UCST and its customer base will enhance the impact and effectiveness of the collaborative efforts of the NGIs, VRCs and individual researchers. Secondly, the overarching goal for UCST is to make the NGIs aware of the services that are being put in place for them and to promote these such that it becomes the norm for NGI User Support Teams to use them. Thirdly, development of the Technical Services for Users and Communities will underpin a growing take up by the many of solutions provided for the few – such as a ‘Training Marketplace’, the Applications DataBase and a Software Repository.

- Copyright notice

Copyright © Members of the EGI-InSPIRE Collaboration, 2010. See www.egi.eu for details of the EGI-InSPIRE project and the collaboration. EGI-InSPIRE (“European Grid Initiative: Integrated Sustainable Pan-European Infrastructure for Researchers in Europe”) is a project co-funded by the European Commission as an Integrated Infrastructure Initiative within the 7th Framework Programme. EGI-InSPIRE began in May 2010 and will run for 4 years. This work is licensed under the Creative Commons Attribution-Noncommercial 3.0 License. To view a copy of this license, visit http://creativecommons.org/licenses/by-nc/3.0/ or send a letter to Creative Commons, 171 Second Street, Suite 300, San Francisco, California, 94105, and USA. The work must be attributed by attaching the following reference to the copied elements: “Copyright © Members of the EGI-InSPIRE Collaboration, 2010. See www.egi.eu for details of the EGI-InSPIRE project and the collaboration”.  Using this document in a way and/or for purposes not foreseen in the license, requires the prior written permission of the copyright holders. The information contained in this document represents the views of the copyright holders as of the date such views are published.

- Delivery Slip

|  | Name | Partner/Activity | Date |
| --- | --- | --- | --- |
| From | Stephen Brewer | EGI.eu | 22-02-2011 |
| Reviewed by | Moderator: Reviewers: <<To be completed by project office on submission to AMB/PMB>> |  |  |
| Approved by | AMB & PMB <<To be completed by project office on submission to EC>> |  |  |

- Document Log

| Issue | Date | Comment | Author/Partner |
| --- | --- | --- | --- |
| 1 | 22-02-2011 | First draft | Stephen Brewer/EGI.eu |
| 2 | 09-03-2011 | Content added | Stephen Brewer/EGI.eu |
| 3 |  |  |  |

- Application area

This document is a formal deliverable for the European Commission, applicable to all members of the EGI-InSPIRE project, beneficiaries and Joint Research Unit members, as well as its collaborating projects.

- Document amendment procedure

Amendments, comments and suggestions should be sent to the authors. The procedures documented in the EGI-InSPIRE “Document Management Procedure” will be followed:
https://wiki.egi.eu/wiki/Procedures

- Terminology

A complete project glossary is provided at the following page: http://www.egi.eu/about/glossary/.

- PROJECT SUMMARY

To support science and innovation, a lasting operational model for e-Science is needed − both for coordinating the infrastructure and for delivering integrated services that cross national borders.

The EGI-InSPIRE project will support the transition from a project-based system to a sustainable pan-European e-Infrastructure, by supporting ‘grids’ of high-performance computing (HPC) and high-throughput computing (HTC) resources. EGI-InSPIRE will also be ideally placed to integrate new Distributed Computing Infrastructures (DCIs) such as clouds, supercomputing networks and desktop grids, to benefit user communities within the European Research Area.

EGI-InSPIRE will collect user requirements and provide support for the current and potential new user communities, for example within the ESFRI projects. Additional support will also be given to the current heavy users of the infrastructure, such as high energy physics, computational chemistry and life sciences, as they move their critical services and tools from a centralised support model to one driven by their own individual communities.

The objectives of the project are:

- The continued operation and expansion of today’s production infrastructure by transitioning to a governance model and operational infrastructure that can be increasingly sustained outside of specific project funding.

- The continued support of researchers within Europe and their international collaborators that are using the current production infrastructure.

- The support for current heavy users of the infrastructure in earth science, astronomy and astrophysics, fusion, computational chemistry and materials science technology, life sciences and high energy physics as they move to sustainable support models for their own communities.

- Interfaces that expand access to new user communities including new potential heavy users of the infrastructure from the ESFRI projects.

- Mechanisms to integrate existing infrastructure providers in Europe and around the world into the production infrastructure, so as to provide transparent access to all authorised users.

- Establish processes and procedures to allow the integration of new DCI technologies (e.g. clouds, volunteer desktop grids) and heterogeneous resources (e.g. HTC and HPC) into a seamless production infrastructure as they mature and demonstrate value to the EGI community.

The EGI community is a federation of independent national and community resource providers, whose resources support specific research communities and international collaborators both within Europe and worldwide. EGI.eu, coordinator of EGI-InSPIRE, brings together partner institutions established within the community to provide a set of essential human and technical services that enable secure integrated access to distributed resources on behalf of the community.

The production infrastructure supports Virtual Research Communities (VRCs) − structured international user communities − that are grouped into specific research domains. VRCs are formally represented within EGI at both a technical and strategic level.

- EXECUTIVE SUMMARY

The first year of the EGI-InSPIRE project has seen the establishment of the User Community Support Team at the EGI.eu headquarters in Amsterdam and through this team, the user and community support functions have been robustly defined.  The team’s role within the broad context of the European Grid Infrastructure (EGI) has been to harness the efforts and needs of traditional and emerging new communities, thereby creating a collaborative environment where efforts are pooled to the clear benefit of scientific researchers across Europe.  Strong working relationships have been cultivated with the National Grid Initiative (NGI) Support Teams as well as with emerging Virtual Research Communities (VRC) whereby we can communicate and support communities of researchers with common interests and practices. The biggest challenge has been the lack of funded projects to help coalesce the domain-specific user communities which has led to weaker than expected sustainability plans emerging from some of these Heavy User Communities.

For Year 2 of the project, three key areas of work have been planned.  Firstly, even stronger communication between the UCST and its customer base will enhance the impact and effectiveness of the collaborative efforts of the NGIs, VRCs and individual researchers.  Secondly, the overarching goal for UCST is to make the NGIs aware of the services that are being put in place for them and to promote these such that it becomes the norm for NGI User Support Teams to use them.  Thirdly, development of the Technical Services for Users and Communities will underpin a growing take up by the many of solutions provided for the few – such as a ‘Training Marketplace’, the Applications DataBase and a Software Repository.

TABLE OF CONTENTS

1	Introduction	7

2	User Community Coordination	8

2.1	UCST: the role and achievements of the User and Community Support Team	9

2.2	NGI User Support Teams	12

2.3	Technical Services for Users and Communities	13

2.3.1	Training Events and Training Repository: the “Training Marketplace”	14

2.3.2	The Applications Database (AppDB)	14

2.3.3	VO Services	16

2.3.4	The Dashboard Framework	18

2.3.5	The Community Software Repository	18

3	Plans for the next year	20

3.1	User and Community Support Team	20

3.2	NGI User Support Teams	21

3.3	Technical Services for Users and Communities	22

3.3.1	Training Events and Training Repository: the “Training Marketplace”	22

3.3.2	The Applications Database (AppDB)	22

3.3.3	VO Services	23

3.3.4	The Community Software Repository	23

4	Conclusions	24

5	References	25

# Introduction

This document presents a summary of the achievements of the User Community Support activity during the first year of the EGI-InSPIRE project, an analysis of the issues that have emerged together with any remedial action and finally a set of plans for the second project year. User Community Coordination is led by a team based at the EGI headquarters in Amsterdam in the Netherlands and augmented by a distributed team of developers based across a number of EGI partners namely GRNET, STFC and LIP (in conjunction with UPVLC through IBERGRID).

The users of the EGI infrastructure have traditionally come from communities that have been heavily involved in developing the underlying technology and hence have possessed the knowledge and skills to exploit and further develop the grid. However, this is rapidly changing and for a number of reasons. The role of the User Community Support activity within EGI is to harness the efforts and needs of these emerging new communities and, together with those of the traditional communities, create an environment where these needs and efforts are pooled to steer the emerging infrastructure towards a position where users from across Europe and in all disciplines can work and collaborate in ways that suit their research needs without obliging them to become experts in the infrastructure itself. This is partly achieved by providing a suite of services - applications database, VO monitoring tools, training marketplace, community repository - as well as a model of cultivating Virtual Research Communities (VRC) whereby we can communicate and support communities of researchers with common interests and practices.

The activity has cultivated a strong working relationship with the NGI Support Teams in order to maintain another channel into the user communities through integrating the EGI support services with those of the NGIs. This support for the VRCs and NGIs will take the form of workshops and road-shows in addition to the technical services which enable us to tailor resources to the needs of these communities and also disseminate information and knowledge to their needs.  The first round of workshops will build upon the activities of the application developers who are currently known to be active by the NGIs and the research communities. These application developers represent a valuable link to the end users, particularly those who do not wish to have to deal with the complexities of the infrastructure directly.

The User Community Support activity has also worked hard during the course of the first year to define and establish the user and community support function both in terms of subject domain and the geographical reach of the EGI community and eco-system. The biggest challenge has been the lack of funded projects to help coalesce the domain-specific user communities which has led to weaker than expected sustainability plans emerging from some of these Heavy User Communities. However, as we reach the end of the year positive signs are starting to emerge that some of these communities are close to establishing alternative arrangements.

# User Community Coordination

The User Community Coordination activity has reached the end of the year having acquired its full complement of staff, established all of the key services and processes and having substantially achieved the goals and objectives laid down in the DoW.

The WMSMonitor tool used to monitor glite-WMSLB instances status and job flow.(R 14)

The above image shows Professor Alexandre Bonvin, representative of the WeNMR VRC, demonstrating how he uses the WMS monitor to check up on the jobs that his team are running on the infrastructure. In addition to EGI, WeNMR also make use of resources in North and South America, all of which can be monitored on his smart phone.

The EGI User Community Support Team (UCST) essentially comprises a crew that provides coordination and support to the various distributed support teams across the NGIs and other specialist areas including VRCs. The website and other documentation provide guidance and direction to users and communities as to the optimum channels for them to receive help. A suite of technical services has been developed and is provided to augment these support services.

The User Community Support activity also plays a part in capturing and processing requirements from across the community and proactively processing them in order to feed them to the appropriate area for further action. A transparent, accessible Requirements Tracking (RT) system has been implemented into which all members of the EGI community can submit, track and comment on requirements. Requirements can relate to any aspect of the e-Infrastructure form middleware to research applications to support services. Requirements are investigated, analysed and processed by the EGI UCST in conjunction with support team members from the NGIs and other partners. NA3 continues to develop the suite of technical services for users and communities. Discussions have been progressing with a number of geographically distributed user communities with the expectation that a number of these will become VRCs in the near future.

At the time of writing, the Requirements Tracking system has gathered approximately 250 requirements spread across various work packages and drawn from various communities. The system has been swiftly adopted by the different divisions of EGI to facilitate the open tracking and processing of requirements tickets through the different areas and beyond. This has been achieved on the basis of developing strong working relationships with a number of research communities, many of whom are working towards finalising their individual MoUs. Working relationships with the support teams of the NGIs have become more active as they start to see the benefits of both contributing to and making use of the technical services being developed and provided by the EGI UCST.

The User Community Support activity (NA3) benefits from strong interaction with all of the other work packages in the InSPIRE project:

- NA2 – External Relations:

  - Preparation of dissemination material for User Community Support;

  - Blog posting – an informal dissemination channel designed to stimulate discussion;

  - Contributing articles for the Inspired Newsletter;

  - Organisation of training eg “How to talk to the media” which S Brewer attended

  - Preparation of policy for procedures including UCB and USAG;

  - Preparation of MoUs and Letters of Intent (to collaborate as an VRC)

- SA1 – Operations:

  - SA1 has participated in the development and configuration of the Requirements Gathering system and is now making use of this;

- SA2 – Provisioning the Software Infrastructure:

  - SA2 has also been involved in the evolution and uptake of the Requirements;

  - Gathering service particularly in the context of the activities of the TCB;

  - There has been much communication over the year, particularly recent months, relating to the roadmaps of the technology providers in order to maximise the timeliness of activities in NA3;

  - Liaison over the running and development of the helpdesk (GGUS)

- SA3 – Services for the Heavy User Communities (HUC):

  - SA3 provides a communication channel to the HUCs;

  - SA3 provide tools and services for the HUCs which will be made available to others. These include: GANGA and DIANE job submission tools in conjunction with a ‘mini-dashboard’, NGIOS and the Accounting portal;

  - The ORACLE-based Dashboard is hosted at CERN but is available to those users who have developed their own NAGIOS probes.

- JRA1 – Operational Tools:

  - Contact is maintained to evaluate which operation tools may be of interest to the user communities and therefore made available through the VO services.

## UCST: the role and achievements of the User and Community Support Team

UCST has been operating a ‘front desk’ help service since the beginning of the project. By the start of 2011 the staffing had risen to full strength and all of the technical services were available as resources for users. In order to build upon these resources, both technical and human, three channels of endeavour were required. All were challenging, required drive and persistence, and needed coordination and alignment in order to achieve the desired outcome. The desired outcome being an integrated and cohesive support structure to serve the needs of all communities, large and small, both new and established.

The first challenge was that many of the communities that we wanted to support were a long way from being sufficiently organised to communicate as one in the form of a Virtual Research Community (VRC). The Heavy User Communities that were formally incorporated into the project through SA3 did not all manage to resolve the failure of the Specialist Support Centres (SSCs) to get funding. Some, such as WLCG, remained strong in terms of having a ‘voice’ with which UCST could communicate but many of the other contacts reported that they did not have the resources to take on the responsibility of speaking for their community without specific new project funding to do so. In order to resolve these issues the User Support Coordination activity has been working with the known HUC contacts to reduce the effort that might be required to fulfil this role. Essentially, the purpose of a VRC is simply to capture and articulate the needs of that community and communicate the benefits and services provided by EGI to the users within the community. Therefore, a simple gateway, mailing list and contact address might be sufficient. It is not necessary that a VRC representative is a ‘leader’ of a community, rather a spokesperson who is known and respected within that community. Additionally, a template Letter of Intent was produced to enable candidate VRCs to declare their intention to establish a VRC in order to canvas support from across their community. This was a concept that emerged from the first User Community Board (UCB) meeting to which many of the candidate VRC representatives were invited in November 2010.

The second challenge was that the communication channels within NGIs were sufficiently heterogeneous to entail that it took time to establish the optimum contact points to integrate technical, support and operational contacts for maximum efficiency. This has largely been resolved now with initiatives such as the Training Working group helping to reinforce such communication in specific areas. It is anticipated that the first User Forum will present the perfect opportunity to confirm these connections with face to face meetings across many of those involved in the support function across the EGI community.  The NGI support teams are described in more detail in the following section.

The third challenge was that there were issues with the technical services that meant that they did not evolve as smoothly as we would have liked. The applications database made steady and dependable progress from being a cohesive standalone service from the start to being available as a gadget to be embedded within the EGI Support webpages. The VO services progressed slowly at first as a lengthy investigation was required to determine which tools were available from the other work packages to offer to users and to develop support material for these new users. Additionally the dashboard that had been anticipated to be used as the key service was dependent on the commercial ORACLE database system, a port of the dashboard to an open source database system was not an option. A work around was eventually found and the porting option remains a potential solution if sufficient demand emerges from the user community. Furthermore, the ORACLE-based service run at CERN under SA3 may be available for communities that can produce their own NAGIOS test probes in some circumstances.

On a positive note, good progress was made in all other areas of the activity. These are described below:

Implement, utilise and review the requirements gathering process

A requirements gathering process was defined and the existing EGI RT issue tracking system was configured to process requirements. The advantage of this technology was that it already existed as an EGI service, it was supported, and that knowledge acquired by both NA3 and the IT department in establishing the system could benefit EGI in other areas. A key requirement of the requirement gathering system itself was transparency across EGI and reaching out to user communities and other DCI projects.

This has been achieved. The system is working and in use and is being utilised by other work packages within EGI-InSPIRE and other DCI projects including EMI and IGE. The system has been comprehensively documented in the User Community Coordination section of the EGI wiki:

- https://wiki.egi.eu/wiki/Requirements_gathering_details

Instructions on how to use the Requirements Gathering System can be found here:

- https://wiki.egi.eu/wiki/Requirements_Tracking

During PQ4 this information will be ported to the User Community web pages and presented in a more user friendly manner.

Formalising our working relationship with the research communities in the form of MoUs

Following successful discussions with the various known communities and internal partners a template for an MoU for establishing and running a VRC was produced. This is now available to all partners (R 13). Various of our known contacts are working on tailoring this to their own needs. The first VRC to be established was the Worldwide e-Infrastructure for NMR and Structural Biology (WeNMR) community. A number of other communities are making good progress with developing their own MoUs. This process should speed up as more VRCs are established.

Reaching out to new communities

Leads to new communities can come from various sources. These include direct requests, our own enquiries and investigations as well as introductions and suggestions from partners and other contacts. Such leads have led to on-going discussions with the following communities:

- Hydro-meteorology – through the Distributed Research Infrastructure for Hydro-Meteorology Study (DRIHMS) Project

- Digital Cultural Heritage – through the Digital Cultural Heritage Network (DC-NET) project

- Arts and Humanities – through the Arts and Humanities ESFRI project DARIAH

- Linguistics and language research infrastructure – through the ESFRI project CLARIN.

- ESFRI projects; we continue to be in touch with the following ESFRI projects, either directly or indirectly, to ascertain how we can be of assistance: Lifewatch, ELIXIR, CLARIN and DARIAH.

Training-related requirements

A Training Working Group (TWG)(R 12)1 has been convened to discuss the needs of the EGI community with respect to training and to capture and evaluate these requirements in order to support the effective development of the training ‘Market Place’.  This will ultimately enable users and the user community to respond to the challenges and opportunities arising from the evolution of EGI. The Group is accountable to the UCST under WP3 and its remit is as follows:

- To consider how User Support Teams from the NGIs and other partners can cooperate most effectively from the perspective of the delivery of quality training to as many members of the user community while avoiding duplication and wastage.

- To contribute and discuss training requirements and process these through the UCST Requirements Tracking System.

- To provide feedback to their organisations regarding the processing of training requirements.

The User Support Web site

The User Support website has evolved in steps over the course of the year. The first iteration was formal, somewhat dry, and was structured around the organisational framework of the project rather than the needs of the users. The second iteration was more concise and contained more detailed explanations of everything that the activity offered but the structure of the navigation was not as efficient as it could be. Part of the reason for this was the challenge of embedding the technical services within the Content Management System (CMS) that was used for the website. This was as much a product of the CMS as the current implementation of the technical services. This meant that the technical services had to maintain their own sites which mimicked the look and feel of the EGI site and that their navigation was integrated with the EGI site. By the end of the year GRNET, who lead the Technical Services task, had demonstrated a gadget that enabled the Applications Database to be embedded directly within the EGI CMS. Furthermore, GRNET also demonstrated an interface whereby users could automate the creation of their own gadget tailored to their own needs. This presents another opportunity for a service to help the under-resourced VRCs develop their own tools. It is anticipated that the NGI support teams will also find this to be of use. One of the first tasks for the second project year will be for GRNET to replicate this functionality across the other technical services.

The last iteration of the support webpages took place towards the end of the first project year. The content was updated to reflect the current state of the various services available to users and user communities. The NGI contacts together with the discipline based gateways (including the VRCs and candidate VRCs) where clearly presented and the overall navigation was substantially resolved. The underlying guiding principle for this restructuring was the ITIL service model whereby a single point of entry is established to coordinate all aspects of support.

## NGI User Support Teams

NGIs declared at the end of EGEE that they were capable of serving their local users. Therefore the biggest challenge of EGI was bringing the distributed teams of NGI support staff into post-EGEE processes that can efficiently serve the e-Infrastructure needs of multi-national collaborations. The project put various communication mechanisms in place to enable structured and freeform communication for NGIs with their customers, with each other and with EGI.eu. The prime goal of the EGI User Community Support Team (UCST) for Y1 of the project was to establish these communication channels and to assure the proper flow of information through them for the benefit of both NGIs and scientific user communities. The project has setup and is using the following services to exchange information with NGIs:

- Email lists provide freeform communication mechanisms within the complex landscape of EGI user support:

  - Those who are in the NA3 work package of EGI-InSPIRE are subscribed to the inspire-na3@mailman.egi.eu list. This list is mainly used for collecting and distributing project-related information.

  - The main user support contacts of all (but a few) NGIs are subscribed to the ngi-ust-managers@mailman.egi.eu email list and are listed to the community on the EGI Wiki webpage. This email list is used for collecting and distributing information that relates to the EGI collaboration in the broadest sense and that requires coordinated action within NGIs.

- The EGI Requirement Tracker system to capture users’ and support team’s requirements. More than two hundred demands are already stored in this system, out of which about 50 were submitted by NGI representatives. The fully transparent system involves NGIs not only as ‘requestors’, but also as solution providers. Any SSO account holder can provide answers and complete or partial solutions to any of the requirement tickets. The UCST encouraged NGIs to do so by sending out targeted invitations to those groups that potentially have solutions to some stored requirements. Solutions to many of the requirements are emerging from discussions hosted within the same system.

- The Training Events registry is used by NGIs to inform communities and each other about upcoming EGI-related training courses. 28 European and 18 non-European events are registered in the database during Y1. Moreover, reporting forms are offered for trainers and for trainees to help them capture best practices, successful or less successful initiatives during training courses. Event summaries prepared out of these reports are also shared with EGI partners through the same registry.

- Information about grid-enabled scientific applications, reusable support tools and about application developer experts is stored within the EGI Application Database. This is where NGIs and user groups can register their applications, provide details of support experts and can integrate application and developer profiles into community-specific portals and user environments. About 30 new tools and applications have been added to AppDB during Y1.

- Several thousand slideshows, video and audio tutorials and presentations are available under open source licences in the EGI Digital Library. While most of the NGIs are aware of and use the system, recent statistics showed that during Y1 the library has been used only to obtain information but not to share new content with the community. Effort will be made in Y2 to make new training content visible through this service.

- The User Community Coordination section of the EGI Wiki system provides scratch spaces for communities to develop documents, descriptions and manuals collaboratively, before making these entities visible to the general public through the EGI User Support website. While most of the content in this Wiki is written by EGI.eu and by NGIs with international tasks, the Wiki is heavily used by NGIs as a rich source of information.

- The EGI blog is a new service that provides a simple, yet powerful way to alert the EGI community about new developments, solutions or issues that exists within the collaboration. While statistics indicate that NGIs are gradually becoming aware of the blog, most of the posts have been written so far by EGI.eu staff. Effort will be made in Y2 to involve NGI user support teams to write blog posts.

## Technical Services for Users and Communities

Over the course of the first year of the project the disparate technical services that the InSPIRE started have been progressively brought together until the point where they have now coalesced into a cohesive suite of integrated resources that users would want and indeed can use as a package. These are now reviewed separately.

### Training Events and Training Repository: the “Training Marketplace”

The training services consist of a training events calendar and a Digital Library containing training-related material. Both of these systems were inherited from the EGEE project and had been used successfully for many years. The systems have been developed and hosted at the University of Edinburgh both during the EGEE projects and up until now within InSPIRE. Unfortunately, for a number of reasons which did not become unclear until towards the end of the year, this did not turn out to be a satisfactory arrangement. Early in the New Year we learnt that Edinburgh were closing down the department that had been doing this work which explained the unsatisfactory level of commitment from the institution previously. On a positive note the training services continued to run during the course of the year and, to be fair, all three of the technical staff assigned to the work at different times all addressed technical problems when they emerged. What was lacking was a contribution of vision and engagement in the planning process. The Science and Technology Facilities Council (STFC), have now taken on the coordination of this process on behalf of the UK JRU and they assure us that these issues have now been resolved with STFC taking over responsibility for developing and maintaining the services. A new developer has been assigned and it has been agreed that he will visit EGI at the earliest opportunity to be fully briefed in the work.

### The Applications Database (AppDB)

The activities since the beginning of the project have been primarily focused on migrating valuable existing data from the EGEE era into a new system, able to meet the rise of requirements set forth with the introduction of the EGI era, and expanding the quality of the service. The new system was redesigned to provide a minimalistic, yet advanced in terms of functionality user interface. Another important aspect of development was integrating the EGI SSO system with the portal, in order to provide authenticated write-enabled access. Finally, a new support unit was created in GGUS in order to properly address issues concerning the Applications Database (AppDB) service.

More specifically, the EGEE Applications Registry site held c. 250 entries about applications available to the community via the gLite middleware. This data, stored in a DBMS, was transformed and extended during the migration process and stored in a new DBMS featuring relational support and a data model more suitable for the needs of the EGI project. Support for all UMD endorsed middleware was added (gLite, ARC, UNICORE, Globus) and the concept of tools was introduced. Entries marked as tools, represent helper software that may provide QoS, easy-of-use, or additional functionality to the scientific applications stored in AppDB, and which in general does not lead to publications about results of scientific work. The entries of the existing RESPECT programme were thus also ported into the database, making it an even more valuable service for both application developers and end-users.

Another concept introduced was the storing of personal profiles for each individual application developer and researcher, a feature that aims at simplifying the search for application developer experts who possess specialized knowledge.

It is worth mentioning that in order to map data from the RDBMS to the application layer, a PHP API has been implemented, serving as a more robust object model to use in code, according to the MVC architectural pattern that has been chosen. This API may eventually serve as a building base for external parties wishing to implement their own form of the service.

As far as the user interface of the new portal is concerned, it was designed from the beginning with modern minimalistic principles in mind. It features a navigation pane on the left, from where the user selects the action/view of interest, and a data view on the right, where results/details about the selection are displayed. Explanatory tooltips are available for most of the action points of the display, along with intuitive icons, and where that is not enough, pop-up dialogues with help information are available.

In order to provide the user with a consistent and responsive end result, such architectural design patterns and techniques as MVC and AJAX have been employed. To this end, on another level, extensive use of Javascript has been made, and there has been much effort to keep all major browsers compatible with the portal. At this time, MS Internet Explorer is the only major browser whose support is to be considered experimental, in the sense that it has not been yet extensively tested, although expected to be almost 100% operational.

Another important feature of AppDB, around which much of the development effort was concentrated, was providing write-enabled access to registered users, by linking AppDB to the EGI SSO system. By providing authenticated access, users may, amongst others,

- Register new applications, instead of requesting the data be inserted for them by the AppDB support team

- Modify existing application data whenever they deem appropriate

- Edit application associations with people (developers, scientific coordinators, etc.)

This feature is expected to help provide more up-to-date, quality data, since developers will have one less barrier to divide them from it, and it should motivate them into feeling more connected to the data, in terms of ownership.

The second major release (v1.0) of the AppDB was deployed into production in mid-November, featuring write-enabled access; for the first couple of months after, the release's write-enabled feature was restricted only to NGI representatives, in order to test the functionality while minimizing data corruption in case of errors. After the completion of the testing period, with input from Ireland, Switzerland, Norway, Spain, Poland, and the Netherlands, the said functionality became available to all users holding an EGI SSO account, through the release of a minor version (v1.1), which included many bug fixes and enhancements from the testing period feedback.

Among the most prominent features of this minor version, was the beta release of a read-only RESTful Web API, with XML schemata for all major resources (applications, people, publications, etc.) on a dedicated FQDN [R 1, R 3]. The requirement for such an API has stemmed from the need for NGIs and VOs to be able to provide their own localized, custom interfaces to the applications database service, which could, for example, display entries relevant to their county or discipline only, or in their own native language.

By the time of this writing, a second minor version (v1.2) has followed shortly after, featuring, amongst others

- sanitization of existing data,

- 3rd-person profile management by NGI representative and manager roles,

- a demo platform of web gadgets, based on the Web API, which may be used to simplify integration with other portals/CMS', and

- prototype integration with the EGI Operations Portal, by fetching VO data though its XML interface.

The featured web gadgets provide data visualization for the AppDb web API result sets, paging capabilities and user defined search operations. They are constructed in such a way, as to provide high usability to external web portals and can be configured to display specific information from the AppDB, without any change to the structure of the host site. Data and display customization can be achieved by passing  predefined settings to the requested URL of the gadget, thus avoiding the need of any special client side requirement.

Last but not least of the work achieved, the AppDB Support Unit created in GGUS serves as the main communication channel between interested users and the AppDB development/deployment team in order to communicate bugs, and to help resolve issues concerning the quality of the service. Feature requests, on the other hand, are handled by the EGI RT [R 2] ticketing system, and monitored by the UCST.

Usage of the Applications Database in February 2011 with Italy factored out (70% of the applications originate from Italy for legacy reasons.)

At the end of February 2011 there were 521 applications in the AppDB of which 366 originated from Italy. This is largely a legacy issue due to the fact that during the EGEE era the applications database was developed in Italy.

### VO Services

The VO Services activities focus on assisting the task of setting up and operating a VO. Those are complex tasks that require an important effort for ensuring a high quality of services. Many tools and services are available in EGI that rely on the VO information, and sometimes, procedures are neither easily available nor complete. The EGI VO Services subtask supports VOs in the whole process of start-up, management and operation, pointing out to tools, services, documentation and procedural guidelines to maximize the usage of the resources. The VO services activity is carried out by LIP in Portugal and UPV in Spain. The activities are summarized in four main points:

| - VO Management Support. To set up a central point with procedures, FAQs and a single contact point. - Promote VO activities. To ease the access to tools and services to foster production quality by the users of a VO. - VO Infrastructure Monitoring. To aid setting up tools for monitoring the resources under the VO. - VO Infrastructure Usage. To support the monitoring on the usage of the resources by the users from a VO or a VRC. | Figure 1: Vo Services activities. |
| --- | --- |

In the different activities above mentioned, UPV and LIP have produced the following results:

- VO Management Support.

  - An inventory of basic services has been made (with a proper cost analysis from the operation point of view) required to support VO infrastructures. On the other hand, a set of monitoring and accounting tools that are widely available for new communities was evaluated. All findings are summarised in reports and will be used to define a core set of services that EGI may offer for new communities to simplify and catalyse their infrastructure usage.

  - The VO registration process has been revised and adapted to the EGI era and to the new release of the CIC portal.

  - The ‘VO services’ support unit has been created in GGUS to help VO managers during the VO registration process; assist VO managers deploying technical services which may simplify their user community access to the infrastructure and promote collaboration within the VO; and bridge VO managers requirements with EGI / NGIs resource providers availabilities.

  - Operation of the VO Services support unit in GGUS handling tickets addressed to that support unit, and linking / involving the appropriate bodies to reach a prompt solution. This specific activity has already originated some requirements to EMI. Start decommission process of obsolete GGUS support units with identical mandates in previous projects.

  - The documentation has been inserted on Wiki pages, namely the VO Services Wiki [R 6], acting as the main source of information for this activity, and the VO Management Frequently Asked Question Wiki [R 7], addressing answers to questions from VO Administrators collected from several sources.

- Promote VO Activities.

  - Analysis, evaluation and discussion of a job monitoring framework built on top of GANGA and DIANE job submission tools, and integrated with mini-dashboard platforms installed at CERN. Production of appropriate documentation on the overall framework to guide the discussions [R 8].

  - Other tools for operating a VO are under analysis and use cases, recommendations on usage and links will be provided.

- VO Infrastructure Monitoring.

  - Analysis of the regional NAGIOS framework, and study the possibility to used it as a monitoring tool for the VO infrastructure. Interactions with the regional NAGIOS developers to understand how the topology generation could be changed so that multiple VOs could be monitored under the same box, and how to generate the VO infrastructure topology instead of the NGI infrastructure topology. Deployment of a test box [R 9] supporting two simultaneous test VO. Start to document the overall changes and process.

  - Two test deployments of the service (UPV and LIP) are being performed to transitory host emerging VOs.

- VO Infrastructure Usage.

  - Meetings and discussion with the TSA3.2.1 staff in order to clarify the dashboard framework, and the showstopper originated by the use of ORACLE database solutions. The fact that TSA3.2.1 staff argues that the current dashboard frameworks cannot be ported to open source backends presently prevents this task from progressing.

  - Integrated views of other tools are being considered.

  - The Accounting portal of EGI has been analysed and contacts have been made with the developers to define a requirement to support the integrated view of all the VOs from a VRC.

Finally, and concerning coordination and dissemination, the following actions have been performed:

  - Presentation of the technical support services at the EGI technical forum in Amsterdam.

  - Elaboration of the VO Services six month plan. Presentation [R 4] and discussion of the VO Services six month plan on the first EGI User Support Advisory Group meeting held in November [R 5].

  - Abstract submission and reviewing to the EGI User Forum Conference.

  - Participation in NA3 teleconferences and in other integration meetings.

  - Participation in the NA3 F2F meeting in Amsterdam in March.

  - Collaboration in the review of deliverables.

### The Dashboard Framework

SA3 have contributed this description of the dashboard framework. All Experiment Dashboard applications are developed using the Dashboard framework, which is implemented in Python. The Dashboard framework defines the structure of Dashboard modules. It provides the build system and a common implementation of the main components of monitoring applications and services. The typical structure of a Dashboard application consists of information collectors, a data repository, normally implemented using Oracle database technology, and user interfaces. Information from data sources can be transmitted to the Dashboard application via various protocols. In most cases, the Dashboard application uses asynchronous communication between the data sources and data repository.  Dashboard agents are the components that have to perform regular tasks. Examples of such tasks are: collecting monitoring data, aggregating statistics, analysing statistics, sending alarms, etc. The framework provides all necessary tools to manage and monitor Dashboard agents.

### The Community Software Repository

Preliminary discussions have been made during the first year of the project, about the implementation of the EGI Community Software Repository service. The outcome of these discussions was that, the EGI Community Software Repository service, should be mainly based on already existed services offered by the EGI and the effort needed for such an implementation should be considered as a combined effort offered by both, the NA3 and the SA2 activity. Following these directions, IASA/GRNET team (the responsible team for the AppDB service and also one of the main developers of the EGI Repository) made a proposal of using the AppDB service (provided by NA3) as the front-end medium for the submission of new releases of the registered applications/tools, the RT instance (provided by SA2) for covering a lightweight release verification process and a separate instance of the EGI Repository (provided by SA2) to hold and manage the community related SW releases. This proposal it is still under evaluation.

# Plans for the next year

This section presents the goals for the year ahead together with the broad plans and tasks that will be undertaken to achieve this. This detail will be presented on the Support web pages and comments and feedback is always welcome. The requirements gathering process exists to enable users and user communities to influence these plans through the formal mechanism of the USB and, at a technical level, the USAG. If necessary, plans can be reviewed and this information will be made public through the website and other channels.

## User and Community Support Team

This task exits to draw all of the activities together and deliver them to the users. Although it is within the first year of the project, the first User Forum will occur after this first annual report has been written so it is worth emphasising that this is, in many ways, the culmination of the first year’s work. The forum schedule coupled with the book of abstracts indicate a rich and compelling proposition which should be of interest and value to the whole spectrum of our audience: users, communities, application developers, NGI support teams and more. To reinforce this, the User Community Coordination activity will have its own booth at the User Forum. This will be an opportunity to present this work in addition to that of the NGI support teams and the VRCs.

In order to drive forward the user facing perspective of the infrastructure we will deliver the following ten point action plan:

- Website to draw in all categories of users (www.egi.eu/user-support)

The website will continue to evolve in terms of usability and as a hub for all information about our work and services for all categories of users.

- Gather intelligence: metrics, data, trends, knowledge, geo-spatial information

UCST will continue to capture metrics about all aspects relating to the user communities in order to optimise services and information to their needs.

- Investigate key requirements – share knowledge with users/developers/middleware providers

UCST will continue to proactively investigate requirements and report in a meaningful way on the emerging results of these investigations in order to maximise the efficiency of all involved in this endeavour

- Blog – post updates on all aspects of NA3 to stimulate discussion

UCST has established itself as the dominant contributor to the EGI blog service as revealed by the tag cloud and the Google Analytics dashboard and will strive to maintain this position. The blog represents a discussion forum for the user community to interact in a public arena with the members of the UCST. We welcome and will encourage such discussions.

- Meet the Application Developers – workshops to support key topics

End users, the scientists and other researchers who use the grid increasingly do not want to know or have to know about the workings of the infrastructure itself. Application developers are the bridge between such users and the infrastructure. Through the applications Database we already have contact points for over 500 developers. Through supporting developers to enrich the user experience with more and better gateways, portals, applications and tools we can beneficial serve the needs of users, communities as well as the NGI support teams.

- EGI Community Roadshow – in conjunction with NGIs (after NGS)

For a number of years the UK’s NGI, the NGS has organised a series of roadshows at various locations around the UK. We plan to replicate this successful model on a European level and design a format that can be replicated in each country in conjunction with the local NGI support teams and the dominant research community in the particular country.

- Training ‘marketplace’ – combined Training Calendar and Digital Library

One of the most significant limitations of the technical services at the start of the project was the decoupled nature of the resources. Once you had identified an application of interest you had to then go into the training database and search for related training material and separately again search the calendar for related events. All of the services have APIs, the goal now is to harmonise these and integrate the services.

- Video material & online courses for training – supply tools and support

There is very little new material in the training database. This is already being addressed with ta drive to encourage all parties to submit their material or at least links to their material. As we ramp up this effort we will provide help and advice on how to produce the best training material and also provide support and tools for developing online resources and video material. This will draw upon the links with InSPIRE’s sister project e-Science Talk.

- Key figures: identify influential figures in communities and support them

A number of other projects have successfully run schemes whereby they champion influential figures in the community. We will identify some key figures within different research disciplines who can champion the EGI user community activities and provide them with additional support.

- Technical Services: APIs, portlets and apps for gateways and smart phones

We will continue to develop the technical services and ensure they form a compelling and integrated suite of resources that meet the ever increasing demands of grid users both established and new.

## NGI User Support Teams

The overarching goal for Y2 is to make the NGIs aware of the services that exist for them and making these solutions routinely used by the NGI User Support Teams, in order to make their work more visible for members of the EGI collaboration. The Technical Services together with the recently restructured User Support Webpage and the recently established EGI blog will be important tools in achieving this goal. Monitoring the usage of these sites is therefore a key to later evaluate the success of the promotion activity. The ‘NGI roadshow model’ will also help EGI to promote NGIs’ services and to inform NGIs about the tools that exist for them.

In order to better understand the services of NGIs and the relationship of NGIs with technical services, communication services as well as with user communities, the EGI.eu User Community Support Team has issued a Survey to NGI User Support Teams at the end of February. The survey is open until the middle of March, but the preliminary findings (21 answers until 07/03/2011) show that the answers will trigger the following set of actions:

- Rationalisation of services that are provided for NGI user support teams in order to better meet the users’ needs and to better integrate into the support workflows of the NGIs.

- Refocusing and integrating the support activities that NGIs provide to scientific projects, primarily to ESFRI project.

- Improving the visibility of NGIs through the EGI.eu webpage, by adding entry points that drive users directly to national support teams.

- Improving the visibility of reusable tools and applications that the NGIs developed for end users and for user support teams.

## Technical Services for Users and Communities

The plans for the Technical Services are described below. The Task and sub-Task leaders for this activity will continue to meet on a Wednesday afternoon by telephone on alternate weeks to drive forwards these activities and also to work towards the tighter integration of the services as well as their delivery and promotion.

During the first year of the project, due to the complexity of some aspects of the various technical services which have been described earlier, much of the coordination of the technical services task had to be driven by activity leader. Now that these issues have been, we  trust, resolved and the entire distributed NA3 team is working as a cohesive whole, it is anticipated that GRNET will be able to take over this coordinating role as planned and be able to focus on the technical challenges ahead.

### Training Events and Training Repository: the “Training Marketplace”

This activity has just, at the time of writing of this report, been taken over by STFC. The new developer assigned to the work will visit EGI at the earliest opportunity. Claire Deveroux, who manages the activity will maintain close contact with the activity in all aspects of the work both technical and in terms of its usage.

STFC have already taken delivery of a detailed requirements report that was prepared by UCST. This was used at the planning stage for the migration to STFC and will form the basis of the product development plans that STFC are working on.

### The Applications Database (AppDB)

Current development on the AppDB service is still according to the workplan specified at the first USAG meeting [R 11]. However, priority changes have been made to meet the circumstances, and additional items have been injected, in order to meet the rise of requirements from the evaluation of new user stories.

Our main priority for the year to come will be the fulfilment of pending items from the first year, such as enhancements to the data/object model, usability, and quality of service and information, as those have been already defined in [R 10]. Once these items have been satisfied, further development will focus on the following guidelines:

- Data review and evaluation, by contacting application contributors. The UCST's involvement in this action is expected to play a crucial role.

- Integration with other application databases, such as GISELA and EPIKH. A technical specification for data synchronization procedures is expected to be needed.

- Integration with the EGI Community Software Repository. Developers should be able to register and submit software releases and associated metadata of their applications through the AppDB interface, for storage in the repository, which end-users would in turn be able to easily find and download. Such a feature would help further establish the AppDB's role within EGI, since the information provided will be more than just metadata about software, but - in a sense - the actual software itself.

When a satisfactory level of the aforementioned items is deemed to be completed, a feature freeze would be advantageous, in order to give the development team the opportunity to audit the existing codebase, and perform what will surely be much needed clean up and optimization procedures. Such an action will help eliminating bugs, boost performance, and solidify security.

### VO Services

The activity of the UPV and the LIP will concentrate in the following items:

- VO Management Support. Continue with the support of the GGUS support unit and on the development of the documentation supporting VO managers. Create a VO Services website to integrate all the information and to gain visibility.

- Promote VO Services. To include additional services recommendations for data access. To integrate services’ information on a consolidated entry point.

- VO infrastructure Monitoring. To deploy VO-NAGIOS boxes for new emerging VOs through the UPV and LIP deployments.

- VO Infrastructure Usage. To follow-on the changes on the accounting portal and to interface it through the VO services website for easing the selection of consolidated VOs.

### The Community Software Repository

Concerning the EGI Community Repository the following activities are expected to be realized in the second year of the project:

- Development/deployment of the Community Repository based on the work done on the EGI Software Repository (SA2)

- Integrate the with the part of the RT module of the Community Repository with the AppDB service

- Development of a web interface for the Community repository (this effort should be also considered as a common task between the SA2 & NA3 activities)

# Conclusions

The first year of the EGI-InSPIRE project has seen the successful establishment of the User Community Support Team at the EGI.eu headquarters in Amsterdam.  Through this team, the user and community support functions, procedures and processes have been put in place.  A collaborative environment where efforts are pooled to the clear benefit of scientific researchers across Europe is becoming increasingly effective and strong working relationships have been cultivated with the National Grid Initiative (NGI) Support Teams as well as with emerging Virtual Research Communities (VRC). The biggest challenge has been the lack of funded projects to help coalesce the domain-specific user communities which has led to weaker than expected sustainability plans emerging from some of these Heavy User Communities.

For Year 2 of the project, three key areas of work have been planned:

- Stronger communication between the UCST and its customer base will enhance the impact and effectiveness of the collaborative efforts of the NGIs, VRCs and individual researchers.

- UCST will aim to make the NGIs aware of the services that are being put in place for them and to promote these such that it becomes the norm for NGI User Support Teams to use them.

- Development of the Technical Services for Users and Communities will underpin a growing take up by the many of solutions provided for the few – such as a ‘Training Marketplace’, the Applications DataBase, VO Services and a Software Repository.

# References

| R 1 | Applications Database API http://appdbpi.egi.eu |  |
| --- | --- | --- |
| R 2 | EGI RT ticketing system http://rt.egi.eu |  |
| R 3 | Applications Database API documentation https://wiki.egi.eu/wiki/TNA3.4_AppDB_REST_API_v0.1 |  |
| R 4 | https://www.egi.eu/indico/getFile.py/access?contribId=2&resId=0&materialId=slides&confId=223 |  |
| R 5 | https://www.egi.eu/indico/conferenceDisplay.py?confId=223 |  |
| R 6 | https://wiki.egi.eu/wiki/VO_Services |  |
| R 7 | https://wiki.egi.eu/wiki/VO_Management_FAQS |  |
| R 8 | https://wiki.egi.eu/w/images/1/15/Diane_Ganga_Evaluation_v2.pdf |  |
| R 9 | https://nagios01.ncg.ingrid.pt/nagios |  |
| R 10 | Specification of Requirements for EGI Applications database https://documents.egi.eu/document/275 |  |
| R 11 | EGI Applications Database Activities Summary and Workplan https://documents.egi.eu/document/276 |  |
| R 12 | https://wiki.egi.eu/wiki/Training_Working_Group |  |
| R 13 | https://documents.egi.eu/document/87 |  |
| R 14 | https://twiki.cnaf.infn.it/twiki/bin/view/WMSMonitor/WebHome |  |

ITIL stands for Information Technology Infrastructure Library - http://www.itil-officialsite.com/AboutITIL/WhatisITIL.asp

OMII-UK and the Software Sustainability Institute (SSI) in the UK have done this with their PALS programme.