EGI.eu

TCB requirements Management

| Document identifier | EGI-TCB-Requirements_Management-V5 |
| --- | --- |
| Document Link | https://documents.egi.eu/document/440 |
| Last Modified | 25/10/2011 |
| Version | 3 |
| Policy Group Acronym | TCB |
| Policy Group Name | Technology Coordination Board |
| Contact Person | Michel Drescher, Michel.Drescher@egi.eu |
| Document Type | Procedure |
| Document Status | REVIEW |
| Approved by | Body who approved the doc |
| Approved Date | DD/MM/YYYY |

Policy Statement This document describes the management process of how the TCB assesses, analyses and takes action on requirements that are brought to its attention for Face-to-Face (F2F) discussions. It defines timelines, responsibilities, and actions that must be taken to ensure a steady and well-documented procurement of assessment and implementation of requirements by the Technology Providers that are represented in the TCB.

Copyright notice

Copyright © EGI.eu. This work is licensed under the Creative Commons Attribution-NonCommercial-NoDerivs 3.0 Unported License. To view a copy of this license, visit http://creativecommons.org/licenses/by-nc/3.0/ or send a letter to Creative Commons, 171 Second Str]eet, Suite 300, San Francisco, California, 94105, USA.

The work must be attributed by attaching the following reference to the copied elements: “Copyright © EGI.eu (www.egi.eu). Using this document in a way and/or for purposes not foreseen in the license, requires the prior written permission of the copyright holders. The information contained in this document represents the views of the copyright holders as of the date such views are published.

Authors list

|  | Name | Partner/Activity/Organisation/Function | Date |
| --- | --- | --- | --- |
| From | Michel Drescher | EGI.eu/Technology Manager |  |

Delivery Slip

|  | Body | Date |
| --- | --- | --- |
| Reviewed by | TCB | DD/MM/YYYY |
| Approved by | EGI.eu Director | DD/MM/YYYY |

Document Log

| Version | Date | Comment | Author/Organization |
| --- | --- | --- | --- |
| 1.0 | 28-03-2011 | First draft | Michel Drescher, EGI.eu |
| 2.0 | 04-04-2011 | Updates after review, DocDB persistence | Michel Drescher, EGI.eu |
| 3.0 | 15-10-2011 | Update after second review (TCB-7) | Michel Drescher, EGI.eu |
| 4.0 |  |  |  |

Application area

This document is a formal EGI.eu policy or procedure applicable to all participants and associate participants, beneficiaries and Joint Research Unit members, as well as its collaborating projects.

POLICY/procedure amendment procedure

Reviews and amendments should be done in accordance with the EGI.eu “Policy Development Process” (https://documents.egi.eu/document/169).

ORGANISATION SUMMARY

To support science and innovation, a lasting operational model for e-Infrastructure is needed − both for coordinating the infrastructure and for delivering integrated services that cross national borders.  The objective of EGI.eu (a foundation established under Dutch law) is to create and maintain a pan-European Grid Infrastructure in collaboration with National Grid Initiatives (NGIs) in order to guarantee the long-term availability of a generic e-infrastructure for all European research communities and their international collaborators.

In its role of coordinating grid activities between European NGIs, EGI.eu will:

- Operate a secure integrated production grid infrastructure that seamlessly federates resources from providers around Europe

- Coordinate the support of the research communities using the European infrastructure coordinated by EGI.eu

- Work with software providers within Europe and worldwide to provide high-quality innovative software solutions that deliver the capability required by our user communities

- Ensure the development of EGI.eu through the coordination and participation in collaborative research projects that bring innovation to European Distributed Computing Infrastructures (DCIs)

The EGI.eu is supporting ‘grids’ of high-performance computing (HPC) and high-throughput computing (HTC) resources. EGI.eu will also be ideally placed to integrate new Distributed Computing Infrastructures (DCIs) such as clouds, supercomputing networks and desktop grids, to benefit the user communities within the European Research Area.

EGI will collect user requirements and provide support for the current and emerging user communities. Support will also be given to the current heavy users of the infrastructure, such as high energy physics, computational chemistry and life sciences, as they move their critical services and tools from a centralised support model to one driven by their own individual communities.

The EGI community is a federation of independent national and community resource providers, whose resources support specific research communities and international collaborators both within Europe and worldwide. EGI.eu, coordinator of EGI, brings together partner institutions established within the community to provide a set of essential human and technical services that enable secure integrated access to distributed resources on behalf of the community.

The production infrastructure supports Virtual Research Communities − structured international user communities − that are grouped into specific research domains. VRCs are formally represented within EGI at both a technical and strategic level.

Executive Summary

This document defines the process how the TCB and its members are managing requirements in need of technical and strategic coordination of technology at a management level.

The requirements management process is fundamentally partitioned into four phases. Beginning with the elicitation and engineering of requirements, the process implements a two-pass filtering and assessment function to decide whether:

- A requirement should be managed through the TCB, or

- Technology Providers shall be mandated to implement a requirement or a collection of those at once with a given priority.

This process document defines activities and processes that are interconnected through time and artefacts to provide a repeatable, clear and transparent requirements management process.

Beginning with an introduction in section 1 the reader will learn about the general concepts of requirements management in EGI, and the design of the four fundamental phases of requirements management in EGI.

Section 2 provides an overview of how the requirements management process is applied to the TCB and related EGI management bodies are contributing to the overall requirements management effort in EGI.

Section 3 provides in-depth information about the process itself. Grouped by major phase of the process, each activity is described through a summary of its purpose and actions, and a clear definition of the expected outcome. This is complemented with the definition of the states a requirement may assume during its lifetime within the TCB requirements management process. The section concludes with a time-line oriented view of the interactions of the various stakeholders of the processes described in this document.

Section 4 describes the documents and auxiliary artefacts that are used in the process. Heavily referenced in other parts of this document this section gives information about the type and intended semantics of the information provided in the process documents.

Section 5 describes a set of criteria that apply to requirements that should be taken up by the TCB to be managed. At large, the TCB expects that many more requirements are elicited and eventually implemented by Technology Providers. However, only a subset of these requires discussion and management on the TCB level. This section may be used as a guide to assess whether to submit requirements to the TCB or not.

The document concludes with a list of references in section 6, and an appendix referencing process tools that support the TCB requirements management process.

Table of Contents

1	Introduction	7

2	Overview	8

2.1	Process requirements	8

2.2	Requirements and Topics	9

3	TCB requirements management process	10

3.1	Requirements engineering	10

3.2	Requirements analysis	11

3.2.1	Submit requirements	12

3.2.2	Analyse requirements	12

3.2.3	Assessment	13

3.3	Requirements delivery	13

3.3.1	Prioritise requirements	14

3.3.2	Implement requirements	15

3.4	Provisioning the software	15

3.4.1	Provisioning	16

3.4.2	Update requirements	16

3.5	Requirements lifecycle and states	17

3.5.1	Submitted	17

3.5.2	Endorsed	17

3.5.3	In Clarification	17

3.5.4	Assessed	18

3.5.5	Planned	18

3.5.6	Delivered	18

3.5.7	Returned	18

3.6	Process and activity timeline	18

4	Process documents & artefacts	19

4.1	Requirements	19

4.2	Catalogue of Requirements	20

4.3	Statement of Solution	20

4.4	Requirement priority	21

5	TCB requirements criteria	22

6	References	23

Appendix A Support tools and documents	24

A.1 EGI RT for requirements	24

A.2 TCB requirement status dashboard	24

A.3 Technolog Provider release schedules	24

Table of Figures

Figure 1: The TCB requirements management process	8

Figure 2: Requirements engineering in a nutshell	10

Figure 3: Detailed process for the TCB's first pass on requirements management.	11

Figure 4: Prioritising and implementing requirements	14

Figure 5: Provisioning new or updated software implementing requirements managed by the TCB	16

Figure 6: Requirement states	17

Table of Tables

Table 1: Timeline and ownership of activities in the TCB requirements management process	18

Table 2: Information that needs to be conveyed when formulating requirements.	19

Table 3: Auxiliary requirement information	20

Table 4: Elements of a Catalogue of Requirements	20

Table 5: Elements of a Statement of Solution	21

# Introduction

Regardless the level at which it happens, processing requirements is a recurring process. Albeit consuming a significant amount of time developing and implementing requirements drives the continuous service improvement of EGI’s distributed computing infrastructure service offered to its user communities.

Embedded in EGI’s virtuous cycle encompassing continuous service improvement and development of new services, requirements processing spans several management entities across the whole EGI community and includes the following four high-level activities:

- Requirements Engineering

- Requirements Analysis

- Software Delivery

- Software Provisioning

For the purpose of this document the involved EGI Management boards and related activities are described within the scope and their responsibilities for the aspects of requirements processing in EGI.

Requirements engineering is conducted in close conjunction with the affected communities that use the deployed software. Within EGI the User Community Board (UCB) and the Operations Management Board (OMB) govern the processes that are implemented to generate requirements on various aspects of the deployed software. Typically, the UCB produces requirements that relate to user facing aspects (e.g. new or improved functionality, availability, and reliability requirements), while requirements produced via the OMB cover operational aspects of the same software (e.g. monitoring, accounting, management or deployment requirements).

Within the remit of the Technology Coordination Board’s (TCB) [R 1] lies the requirements analysis; comprising of the analysis itself and the Technology Provider’s assessment of the efforts necessary to deliver the requirements, this activity is the main focus of this document.

Once cost and effort assessments for requirements are known, final prioritisation will determine the order of implementation and eventual delivery of software satisfying those requirements.

Eventually Technology Providers deliver software for deployment onto the EGI production infrastructure. This is described in the EGI Software Provisioning Process [R 2], and touched only where it interfaces with the requirements processing described in this document.

# Overview

Requirements management is a recurring process consuming a significant amount of time. By distributing the involved activities over clearly identified responsible entities, the effort will be shared while at the same time facilitating clear progress reporting back to the main stakeholders of the overall process.

This document focuses on the TCB requirements management process. The EGI communities spend considerable efforts to prepare, group, clarify and prioritise requirements into a format that is easily digestible in a reasonable amount of time by the members of the TCB. A common format and deadline for providing requirements to the TCB is shared, and agreed across the EGI communities ensure efficient, yet asynchronous communication among EGI management bodies. When recommending items to the TCB, the UCB and OMB chairmen shall be cognizant of the sitting’s available time for discussion and avoid overcharging the Agenda for the meeting.

The TCB requirements management process comprises a number of distinct activities that each fall into one of the identified four high-level activities:

- Requirements engineering

- Requirements analysis

- Software delivery

- Software provisioning

Figure 1: The TCB requirements management process

Of those four activities, only the first one does not fall into the remit of the TCB. The relevant EGI Community management boards, i.e. the OMB and The UCB, govern the requirements engineering activities. The following two activities, the Analysis and the Delivery of the requirements are directly executed by the TCB and its delegates, whereas the Provisioning of the Software that satisfies the mandated requirements is governed by the TCB, but implemented and executed by the EGI-InSPIRE SA2 activity. The following sections describe in further detail the processes and required outcomes.

## Process requirements

The exact process model including specific sub-processes, documents and support tools will satisfy the following:

- Each requirement processed by the TCB must be: Documented, Actionable, Measurable, Testable, Traceable, Satisfying (business needs), and Detailed (enough for system design).

- A requirement may be architectural, structural, behavioural, functional or non-functional.

- Requirements are sufficiently disparate to be processed individually or, tracing overlapping community needs, sufficiently congruent to be grouped into a topic of common interest.

- A topic of requirements must be sufficiently defined so that it may be processed as a single requirement.

- The process is lightweight enough avoiding unnecessary burden thus facilitating uptake and process discipline.

- At any point in time progress reporting (including progress timelines) on requirements is possible.

- Responsibility for further actions on any given requirement is clear and unambiguous

- Requirements have a limited, clearly defined lifetime.

## Requirements and Topics

This document introduces the term “Topic” as a means to group requirements of sufficient overlap. Instead of processing those requirements individually, they may be grouped into topics that are backed by the individual requirements stemming from different EGI communities (e.g. different user communities that use computing resources in similar ways). To avoid over-engineering of the requirements Management process, Topics must be engineered to satisfy the process requirements d) and, particularly e). Throughout the document, the term requirement refers equally to single requirements or Topics.

# TCB requirements management process

The following sections describe the business process and how they integrate with each other. Wherever possible, already existing external processes are included and integrated with the TCB requirements management process definition.

## Requirements engineering

At large, requirements engineering in the context of EGI spans the time spent from the realisation of a business need that isn’t satisfied by existing software up to the submission (or re-submission, see below) of a statement of requirements to the TCB for further processing. Though the detailed activities in this phase are out of scope for the processes described in this document, they need to be put into context since they are integrated with the follow-up processes that are in scope for the TCB.

Figure 2: Requirements engineering in a nutshell

The OMB and UCB are the primary EGI management bodies that steer and oversee the requirements engineering within the EGI Community, From the viewpoint of the TCB, the exact processes constituting the EGI requirements engineering are out of scope; however it is worth noting that, essentially, those processes are conceptually parallel until the point in time when requirements are submitted to the TCB.

Those processes (i.e. “1.1 UCB requirements engineering” and “1.2 OMB requirements engineering”) are mandated to produce fully engineered requirements as follows

- Newly incepted requirements

- Requirements for which the TCB has requested further clarification (i.e. to review requirements that are in state “In Clarification”, see section 3.3.3).

This process may include the respective management board’s decision to take requirements offline for which the TCB has asked for clarification. In this case, the decision and the reasons are recorded in the requirement history, and the state is set to Returned.

## Requirements analysis

The second phase in the overall TCB requirements management process comprises of three distinct activities around requirements that are produced by the Engineering activities.

Figure 3: Detailed process for the TCB's first pass on requirements management.

The goal of the analysis phase is to identify the requirements that are truly affecting the whole EGI community and to learn the necessary efforts to implement and deliver the software that satisfies the pertinent requirements.

### Submit requirements

To prepare for the next TCB Face-to-Face meeting, representatives of the OMB and the UCB begin to compile a Catalogue of Requirements (CoR) document enumerating all new requirements (in the sense that they were not submitted to the TCB before), and all those requirements the TCB asked for further clarification.

As Figure 3 indicates, the OMB and UCB representatives will also have to decide which new requirements are eligible for the TCB requirements management process, and which are not. Those that are not eligible are to be further managed, such as bug descriptions and feature requests, should be channelled through the EGI Service Desk infrastructure (i.e. GGUS). Though formally included in the submission activity, this first filtering of requirements does not necessarily have to happen within the remit of this activity, it may have happened earlier. It is included here to stress the fact that requirements entering the process must satisfy a set of criteria (See Section 5) to be taken further in the TCB requirements management process.

The complete CoR document must be submitted at least two weeks before the next TCB Face-to-Face meeting as a non-editable electronic document attached to the respective meeting entry in EGI Indico (https://www.egi.eu/indico/).

Outcome:

The outcome of the requirements submission activity is defined as follows:

- The CoR document is attached to the meeting agenda provided in EGI Indico (https://www.egi.eu/indico/) no later than 2 weeks before the TCB F2F commences.

- All requirements described in the CoR are tracked and managed in EGI RT (https://rt.egi.eu) and visible in the EGI requirements tracking dashboard with the correct status as described below (https://wiki.egi.eu/wiki/Track_UMD_Requirements)

- All requirements described in the CoR must have transitioned as follows:

  - New requirements: 	Undefined ( Submitted

  - Clarified requirements: In Clarification ( Reviewed

  - Other requirements: 	In Clarification ( Returned

### Analyse requirements

Formally this activity commences at the TCB F2F meeting. However, meeting participants are required to prepare so that discussions around the submitted requirements are kept to a minimum.

The focus of the requirements analysis lies on determining whether the individual requirements in the CoR are in scope for the TCB requirements management process. Effectively, this analysis is a first pass filtering mechanism for the TCB before any requirement is handed over to Technology Providers for implementation and delivery. Three possible outcomes of this analysis may cast one of three verdicts for each requirement individually:

- The TCB may decide to endorse a requirement capturing a true need across the EGI community, including the Technology Providers. The decision must be recorded in the meeting minutes.

- The TCB may decide to return a requirement to the originating EGI management body for it to further pursue that requirement offline. The requirement may be re-submitted to the TCB at a later stage according to the TCB criteria (see below). The TCB’s decision, and the reasons for returning the requirement must be recorded in the meeting minutes.

- The TCB may request further clarification before any decision to endorse or return a requirement can be taken. The discussions and specific instructions for the originating EGI management body must be recorded in the meeting minutes.

Outcome:

The outcome of the requirements analysis is defined as follows:

- The TCB F2F minutes contain the decisions, reasons and instructions per requirement (see above for details)

- Endorsed requirements are clearly associated with one or more Technology Providers.

- All affected requirements must have transitioned as follows:

  - Endorsed requirements:	Submitted ( Endorsed
 			Reviewed ( Endorsed

  - Returned requirements:	Submitted ( Returned
 			Reviewed ( Returned

  - Other requirements: 	Submitted ( In Clarification
 			Reviewed ( In Clarification

### Assessment

After a TCB F2F meeting, Technology Providers take over all endorsed requirements and produce an assessment of the necessary effort to deliver the respective requirement in new, or updated software. A Technology Provider may group requirements together in a combined assessment for the purpose of more effective software delivery with less effort or in a shorter period of time.

The assessment of s must be finished at least two weeks before the next TCB F2F meeting commences allowing the meeting participants to prepare appropriately. The details of this process are specific to each Technology Provider hence not further described in this document.

Outcome:

The outcome of the requirements assessment is defined as follows:

- A Statement of Solution (SoS, see section 4.3) for each assessed (group of) requirement(s) is attached to the meeting agenda provided in EGI Indico (https://www.egi.eu/indico/) no later than 2 weeks before the TCB F2F commences.

- All requirements described in the SoS document(s) must have transitioned as follows:

  - Endorsed ( Assessed

## Requirements delivery

The third principal phase in the TCB requirements engineering process deals with the two most important activities in the whole process. In the previous phases, requirements were engineered, reviewed and distilled to a level of specificity and clarity that all follow-up activities may be carried efficiently and ideally without further clarification. The TCB then takes a decision to endorse, or return a requirement (or to request further clarification).

Figure 4: Prioritising and implementing requirements

Having received an extensive assessment of the requirement covering the development effort (including testing and certification), impact and proposed delivery time of the software, the TCB is now in the place to definitively prioritise requirements according to community needs and Technology Provider availability.

### Prioritise requirements

The TCB receives all assessed requirements, and prioritises them into a work plan for the pertinent Technology Provider. This work plan includes not only the freshly assessed requirements, but also all previously planned requirements. In that sense, the prioritisation exercise represents an integration effort of existing, planned requirements, and any new requirements that were endorsed by the EGI Community and assessed by the pertinent Technology Providers.

The prioritisation effort may involve complex discussions around the assigned priority itself, but more so on the effects and consequences for existing, planned requirements, and the work already put into implementing them.

For each (re-)prioritised requirement the rational for the prioritisation must be recorded in the meeting minutes, alongside Technology Provider statements on the anticipated effects on the delivery of the software that satisfies the pertinent requirement.

At this stage, the TCB may decide that based on the assessment of the Technology Provider the respective requirement will not be pursued further by the TCB and therefore return it to the originating EGI community management board. This decision along with the reasoning must be recorded in the meeting minutes.

The outcome of this prioritisation effort is an updated work-plan for Technology Providers that, formally with the conclusion of the TCB F2F meeting, comes into effect and must be followed.

Outcome:

The outcome of the requirements prioritisation is defined as follows:

- Each (re-)prioritised requirement must carry the new priority.

- A recorded and updated list of requirements (including priorities) for Technology Providers to be worked into their work plans and delivery schedules.

- A succinct, recorded list of requirements that the TCB decided to return to the respective EGI community management board.

- All affected requirements must have transitioned as follows:

  - Accepted requirements:		Assessed ( Planned

  - Re-prioritised requirements:	Planned ( Planned

  - Returned requirements:		Assessed ( Returned

### Implement requirements

Technology Providers will take all planned requirements and adjust their work plans and delivery schedules according to the proceedings of the TCB F2F meeting.

The style and manner of implementing software satisfying the planned requirements is entirely Technology Provider-specific and therefore not further described here. However, during this process Technology Providers may be asked to give progress reports on the implementation status to be discussed at TCB meetings (phone conferences or F2F).

The most obvious outcome of the Implementation process is software that is fully tested and certified for production deployment.

Outcome:

The outcome of implementing requirements is defined as follows:

- New or updated software is fully tested and certified by the responsible Technology Provider and ready for production deployment.

## Provisioning the software

This process is mostly governed by the TCB rather being carried out by it. In essence, this fourth and final phase comprises of the EGI Software Provisioning process carried out by EGI-InSPIRE SA2 and some lightweight post-processing after the EGI Software Provisioning process has finished.

Figure 5: Provisioning new or updated software implementing requirements managed by the TCB

### Provisioning

Once the Technology Provider has finished internal testing and certification, they initiate the EGI Software Provisioning process that is already in place and operational use.

This sub-process is described in [R 2] and therefore not covered in this document.

Outcome:

The outcome of the Provisioning is defined as follows:

- Technology Providers have delivered software that implements planned requirements to the EGI Software Provisioning process.

- The delivered software change notes clearly refer to the requirements managed by the TCB requirements management process

- The software is successfully provisioned according to the EGI Software Provisioning process [R 2] with a definitive outcome for each Software Product.

### Update requirements

Based on the outcome of the EGI Software Provisioning process, affected requirements may need to be updated.

Only for those Software Products that were successfully provisioned for production deployment (i.e. having the RT ticket state Production), the implemented requirements need to be updated.

Those Software Products that failed the EGI Software Provisioning process will be taken back by the Technology Provider, reviewed, and re-submitted to the provisioning process until it passes.

Outcome:

The outcome of the Update requirements activity is defined as follows:

- All requirements implemented by successfully provisioned software must have transitioned as follows: Assessed ( Planned

## Requirements lifecycle and states

As stated in section 2.1 requirements have a defined lifecycle. This document focuses on lifecycle and states for requirements as soon as they are in scope for the TCB. That is, the entire lifecycle of requirements in the engineering phases (see Figure 1 for more details) are not described.

Figure 6: Requirement states

### Submitted

Prior to a TCB Face-to-Face meeting, the UCB and the OMB deliver a Catalogue of Requirements (CoR) detailing all outstanding requirements and their current state. Requirements that were not submitted to the TCB before may be included in the CoR, and by this transition with the submission to the TCB to the state Submitted to record their formal proceeding.

### Endorsed

At a Face-to-Face meeting, the TCB participants may decide to endorse a requirement, reflecting the agreement that the pertinent requirement indeed reflects a need of the EGI community and therefore shall be further assessed by Technology Providers for the necessary effort and a proposed development and provisioning schedule to successfully deliver the requirement.

### In Clarification

A requirement in state In Clarification is handed back by the TCB to the originating community management board for further clarification. That is, the TCB decided that the requirement does not match the TCB’s catalogue of requirements criteria (see section 5), for example the requirement may lack specific information, may address low-level issues, etc.

Requirements in state In Clarification may be included in the CoR submitted to the TCB, if the managing body feels the TCB’s instructions for clarification were adequately met.

### Assessed

Technology Providers take endorsed requirements and develop an implementation and deployment strategy for software in order to deliver the requirement. When the Technology Provider has fully assessed the requirement it returns it to the TCB in status Assessed.

### Planned

The TCB prioritises all assessed requirements, and generates through this an implicit work plan for Technology Providers, inherently changing the requirement’s state to Planned. TPs then in turn take all planned requirements and work the advised effort into their roadmaps and development schedule, eventually handing in new and updated software for provisioning.

### Delivered

At some point in time after being planned, a TP delivers software that satisfies a given requirement for provisioning for deployment onto the EGI Production infrastructure. If the software is successfully provisioned, all implemented requirements are by then transitioned into state Delivered.

### Returned

The TCB may decide that a requirement is out of scope for the TCB to deal with. In this case the TCB documents the reason why the requirement is out of scope, and returns the requirement to the originating EGI community in state Returned.

## Process and activity timeline

The following table provides a summary of the actions and their chronological synchronisation around a series of TCB Face-to-Face meetings, following a set of hypothetical set of requirements through its lifetime by referring to the formal process and activity labels used in the figures throughout this document:

| Point in time | TCB | UCB / or OMB | Technology Provider | EGI-InSPIRE SA2 |
| --- | --- | --- | --- | --- |
| Any time before |  | 1. Requirements Engineering |  |  |
| 2 weeks before F2F #1 |  | 2.1 Submit |  |  |
| F2F #1 commences | 2.2 Analyse |  |  |  |
| F2F #1 ends |  |  | 2.3 Assess |  |
| 2 weeks before F2F #2 |  |  |  |  |
| F2F #2 commences | 3.1 Prioritise |  |  |  |
| F2F #2 ends |  |  | 3.2 Implement |  |
| Software released |  |  |  | 4.1 Provision |
| UMD released | 4.2 Update Requirements |  |  |  |

Table 1: Timeline and ownership of activities in the TCB requirements management process

# Process documents & artefacts

In support of this process a number of documents and artefacts are exchanged between the actors. This section provides more detail about the contents of such documents as opposed to the format in which they are delivered, except where specifically mentioned.

## Requirements

This process document extensively refers to requirements. To facilitate efficient communication and collaboration between the actors in the TCB requirements management process certain key elements of requirements help with the core TCB process of requirements analysis, assessment and prioritisation of requirements (see sections 3.2.2, 3.2.3 and 3.3.1, respectively) – not to mention the actual implementation by Technology Providers.

The following gives an overview of the kind of information that must be engineered to a balance of detail and summary to allow for efficient communication within the TCB.

| Type of information | Description |
| --- | --- |
| Name | A short, descriptive name of the requirement capturing the gist with just a few words. May contain a numbering scheme to uniquely identify requirements. A unique requirement ID may be provided but is not necessary. |
| Description | Full description of the problem or of the new requirement of the stakeholders involved; how to be used. |
| Goals and objectives | A prioritised list of functional and non-functional objectives; indicates mandatory and conditional objectives – i.e. a formalised summary of the Description. |
| Impact | Describe the direct business benefits of the requirement. Includes a strategic analysis of the impact on surrounding systems, both positive and negative. |
| Sponsor and stakeholders | An overview of the communities that are to be catered for, i.e. the requestor and other communities that may benefit from the implementation of this requirement |
| Dependencies | Describes factors that may ensure, enhance or limit the successful delivery of the requirement; Dependencies provide for proper Risk Management. |
| Acceptance criteria | Which specific objectives must be met for the EGI community to accept the delivered software? Which are critical acceptance criteria, which are optional? |
| In scope | What is considered to be part of the requirement or the delivered software? |
| Out of scope | What is considered not to be part of the delivery of the requirement? |
| Milestones and timelines | Help managing the planning of the implementation, effort and resources for Technology Providers. |

Table 2: Information that needs to be conveyed when formulating requirements.

Auxiliary information on requirements allow process-related tracking and management of requirements as opposed to engineering and implementation related information:

| Auxiliary information | Description |
| --- | --- |
| Priority | The priority with which the requirement shall be implemented |
| Current status | The current status as defined in section 4. |
| Change history | A complete log of changes including decisions and their reasoning (or the detailed request for information, where applicable) |

Table 3: Auxiliary requirement information

## Catalogue of Requirements

The Catalogue of Requirements (CoR) is essentially a numeration of requirements that are submitted to the TCB for consideration. By contents, a CoR is a further condensation of the included requirements, providing an analysis of related requirements and a quick overview on what is submitted for what reason.

| Type of information | Description |
| --- | --- |
| Name | A name for the Catalogue of Requirements to help identify a specific CoR. |
| Submission date | The date by which the CoR is submitted to the TCB. |
| Executive Summary | A short overview on the contents of the CoR. |
| Requirements numeration | A formal declaration of which requirements (and in which state) are submitted to the TCB. |
| Requirements | A consecutive sequence of requirements providing the information specified in section 5.1 |

Table 4: Elements of a Catalogue of Requirements

## Statement of Solution

Technology Providers assess the requirements handed over by the TCB. The result are Statements of Solutions, allowing the TCB to decide whether to proceed with the implementation of said requirements and with which priority, or to return the requirement to the originating EGI community management board (i.e. UCB or OMB) for them to further pursue the requirement out of bands.

| Type of information | Description |
| --- | --- |
| Name | A name for the Statement of Solution; must be suitable for future reference and identification. |
| Executive summary |  |
| Assessed requirements | A summary of the endorsed requirements covered in the assessment |
| Effort assessment | How much effort is necessary to reach the objectives specified in the referenced requirements within the given or an alternative milestones and timelines. |
| Milestones and timelines | Alternative milestones and timelines may be given, particularly if a SoS aggregates the implementation of more than one requirement in one go. |
| Resources | Team members and size, both core and peripheral; allocated tools and infrastructure. Identifies management contact points different from Technology Provider contact points |
| Risks | Identifies high-level elements, which might pose a threat to the delivery of the solution up to complete failure. |
| Constraints | Identifies elements, which if not available, would seriously impact the delivery of the solution (e.g. resources with relevant expertise, etc.) |
| Assumptions | Any other elements that are believed to positively affect the delivery of the solution. |

Table 5: Elements of a Statement of Solution

A Statement of Solution may contain much more information than anticipated and required in this document, as this depends entirely on the nature of the proposed solution itself.

## Requirement priority

The following priority tokens are defined for use in the Prioritisation activity (see section 3.3.10). Priorities are defined in ascending order, where a priority with a higher numerical value takes precedence over a priority with a lesser numerical value.

| Numerical value | Name |
| --- | --- |
| 0 | Best effort |
| 1 | No priority |
| 2 | Low priority |
| 3 | Medium priority |
| 4 | High priority |
| 5 | Top priority |

# TCB requirements criteria

Over the course of several meetings the TCB agreed to scope requirements that it takes on for management ([R 3], [R 4]). This section identifies criteria by which OMB and UCB may assess whether a requirement may be submitted to the TCB. However, the following criteria are not exhaustive, and may require reviews to further tailor the level of requirements the TCB may wish to deal with.

In no particular order, the criteria are defined as follows:

- The requirement involves more than one Software Product providing distinct computing services

- The requirement involves more than one Technology Provider

- The requirement may cause a non-backwards compatible change of an interface

- The requirement is of strategic nature and may cause a fundamental change in the production infrastructure

- The requirement was previously submitted as a GGUS ticket but got rejected by the Technology Provider (or the responsible Product Team)

- The requirement captures the need for a new Capability offered by the EGI production infrastructure

# References

| R 1 | TCB Terms of Reference (ToR), https://documents.egi.ey/document/109 |
| --- | --- |
| R 2 | MS 508: EGI Software Provisioning Process, https://documents.egi.eu/document/505 |
| R 3 | 4th TCB meeting (F2F), http://go.egi.eu/TCB-4 |
| R 4 | 7th TCB meeting (F2F), http://go.egi.eu/TCB-7 |
| R 5 |  |

Support tools and documents

EGI RT for requirements

EGI RT (https://rt.egi.eu) is used to engineer, track and manage requirements. At that level of access and detail requirements are mainly processed by the UCB, UCST and OMB, and associated communities.

Particularly RT tickets capturing requirements are used as a focused means of communication and engineering until the respective requirement is mature to be submitted for implementation either via GGUS, or for further processing via the TCB.

It s within the remit of those communities and management boards how to use and evolve RT tickets to capture and engineer requirements. However, the TCB does not actively participate in this and requires requirements submitted by shipping a self-sufficient document to the TCB. Preferably in electronic form, the shipped document may provide RT ticket numbers for further in-depth analysis of the respective requirements.

Albeit primarily used and owned by the TCB, the status of a requirement should be tracked in RT for automation purposes and the TCB therefore encourages the maintainers of the corresponding RT queue to capture the requirements states defined in section 3.5 with appropriate means.

TCB requirement status dashboard

The status of requirements managed by the TCB is tracked using the EGI Wiki at the publically accessible address https://wiki.egi.eu/wiki/Track_UMD_Requirements. This makes use of RT capturing the status of requirements, albeit using out-dated values. By accepting this process definition the TCB implicitly requests to update both RT and the Wiki dashboard to reflect the new requirement status values, and priorities.

Technolog Provider release schedules

To be able to reach closure on requirements management in an orderly manner the TCB requires Technology Providers to provide appropriate feedback on the specific requirements new or updated software is implementing.

This feedback shall be provided in regular Release Schedule updates sent by Release Managers to the EGI Software Provisioning management (i.e. EGI.eu Technical Manager, or the EGI.eu Chief Technology Officer).

# Footnotes

There exist innumerable alternatives of software development processes. For EGI, however, the process described in this document proved to work best in the current environment.