EGI-InSPIRE

ACCOUNTING PORTAL ROADMAP v3.0

Document identifier:	EGI-Accounting_Portal_Roadmap_v3.odt
Date:	8/28/12
Activity:	JRA1
Lead partners for deliverable:	CESGA
Document status:	DRAFT
Document link:	http://www.egee.cesga.es/documents

Abstract: This document is intended to provide an overview of the Accounting Portal roadmap including its new working plan and release procedure.

Copyright notice / Copyright © Members of the EGI-InSPIRE Collaboration, 2010. See www.egi.eu for details of the EGI-InSPIRE project and the collaboration. EGI-InSPIRE (“European Grid Initiative: Integrated Sustainable Pan-European Infrastructure for Researchers in Europe”) is a project co-funded by the European Commission as an Integrated Infrastructure Initiative within the 7th Framework Programme. EGI-InSPIRE began in May 2010 and will run for 4 years. This work is licensed under the Creative Commons Attribution-Noncommercial 3.0 License. To view a copy of this license, visit http://creativecommons.org/licenses/by-nc/3.0/ or send a letter to Creative Commons, 171 Second Street, Suite 300, San Francisco, California, 94105, and USA. The work must be attributed by attaching the following reference to the copied elements: “Copyright © Members of the EGI-InSPIRE Collaboration, 2010. See www.egi.eu for details of the EGI-InSPIRE project and the collaboration”. Using this document in a way and/or for purposes not foreseen in the license, requires the prior written permission of the copyright holders. The information contained in this document represents the views of the copyright holders as of the date such views are published. / Delivery Slip / Name Partner/Activity Date / From Alvaro Simon CESGA/JRA1 05/10/11 / Reviewed by Moderator: / Reviewers: / Approved by AMB & PMB / Document Log / Issue Date Comment Author/Partner / 1 05/10/11 First draft (v1.0) entering internal review. A. Simon/CESGA / 2 / 3

Content
# Introduction
## Purpose of the document
This document shows the Accounting Portal new roadmap and its future deliverables and milestones.
## Application area
Readers can use this document to obtain general info about Accounting Portal status and future work.
## references
[R1] http://accounting.egi.eu/	Accountig Portal
[R1] http://accounting-devel.egi.eu/	Accounting Portal (development)
[R3] http://cic.egi.eu	Operations Portal
[R4] https://goc.egi.eu	GOCDB

## Document amendment procedure
This document may be updated as new services are to be included into the Accounting Portal or if new milestones are required.
Comments should be sent to the authors of this document.

# Executive summary
This document covers the “Accounting Portal” service that is installed at CESGA and provides a brief future plan for this global service. This document includes these sections:

WBS, WBS dictionary, list of deliverables, list of milestones and the schedule.

The development is based on the spiral model. Four complete cycles are defined, with a new release of the Accounting Portal at the end of each cycle (after 6 months).

Inside each cycle there are four steps. After each step a preview release including the additional views created will be available in the development version of the Accounting Portal for internal review.

The detailed schedule is presented in Section 8.

# ACCOUNTING PORTAL

The EGI Accounting Portal is the global graphical front-end to EGI accounting data. Accounting statistics are available through this portal for the analysis of the different grid users, VO administrators an site administrators. This data is analysed to generate statistical summaries that are made available through a web interface.

## Project life cycle

It is based on the spiral life-cycle model. Four complete cycles are defined, producing a new release of the Accounting Portal at the end of each cycle (see Figure 1).

Inside each cycle there are four steps: Design, Implementation, Release and Revision.

Figure 1: Development Cycle

After each cycle dedicated meetings will be organized with activity leaders to define the set of views to implement and which are required by the NGIs.

# WBS

MP1	Design
MP2	Implementation
MP3	Release
MP4	Revision

# WBS Dictionary

Code	MP1
Name	Design
Definition	Accounting Portal new design.
Deliverables	DMP3.1.1 DMP3.1.2 DMP4.1.1 DMP4.1.2 DMP5.1.1 DMP5.1.2 DMP6.1.1 DMP6.1.2
Milestones

Code	MP2
Name	Implementation
Definition	Accounting Portal internal improvements and new implementations.
Deliverables	DMP3.2.1 DMP3.2.2 DMP4.2.1 DMP4.2.2 DMP5.2.1 DMP5.2.2 DMP6.2.1 DMP6.2.2
Milestones

Code	MP3
Name	Release
Definition	Accounting Portal production releases, maintenance, OS upgrades and repository synchronization.
Deliverables	DMP3.3 DMP4.3 DMP5.3 DMP6.3
Milestones	MMP3.3 MMP4.3 MMP5.3 MMP6.3

Code	MP4
Name	Revision
Definition	Accounting Portal revision and shop-list review.
Deliverables	DMP1.4 DMP2.4 DMP3.4 DMP4.4
Milestones	MMP3.4 MMP4.4 MMP5.4 MMP6.4

# LIST OF DELIVERABLES
Deliverable	Name	Description
DMP3.1.1	InterNGI usage capabilities v1	Design of InterNGI usage capabilities v1
DMP3.2.1	InterNGI usage capabilities v1 development	Implementation of InterNGI usage capabilities v1
DMP3.1.2	New views	Summary view and other view design and reorganization
DMP3.2.2	New views development	Summary view and other view implementation
DMP3.3	Accounting Portal v4.2 (Fomalhaut)	Accounting Portal release.
DMP3.4	Accounting Roadmap v4	AP Roadmap deliverable.
DMP4.1.1	InterNGI usage capabilities v2	Design of InterNGI usage capabilities v2
DMP4.2.1	InterNGI usage capabilities v2 development	Implementation of InterNGI usage capabilities v2
DMP4.1.2	XML Interfaces v2	New user programmable XML interfaces design
DMP4.2.2	XML Interfaces v2 implementation	New user programmable XML interfaces implementation
DMP4.3	Accounting Portal v4.3 (Giedi)	Accounting Portal release.
DMP4.4	Accounting Roadmap v5	AP Roadmap deliverable.
DMP5.1.1	Contributed CPUs v1	Design of contributed CPUs views.
DMP5.2.1	Contributed CPUs development v1	Development of contributed CPUs v1
DMP5.1.2	Parallel Job accounting v1	Design of new views for parallel jobs using accounting repo database.
DMP5.2.2	Parallel Job accounting development v1	Implement the new parallel Jobs accounting views.
DMP5.3	Accounting Portal v4.4 (Hadar)	Accounting Portal release.
DMP5.4	Accounting Roadmap v6	AP Roadmap deliverable.
DMP6.1.1	Local Jobs accounting v1	Design views for local jobs accounting.
DMP6.2.1	Local Jobs accounting v1 development	Develop new views or queries for local jobs accounting.
DMP6.1.2	Application domain accounting v1	Design and requirements for the application domain accounting.
DMP6.2.2	Application domain accounting implementation v1	Implement new features for the application domain accounting within the Accounting Portal.
DMP6.3	Accounting Portal v5 (Izar)	Accounting Portal release.
DMP6.4	Accounting Roadmap v7	AP Roadmap deliverable.

# LIST OF Milestones

Milestone	Description
MMP3.3	Accounting Portal v4.2 (Fomalhaut)
MMP3.4	Accounting Roadmap v4
MMP4.3	Accounting Portal v4.3 (Giedi)
MMP4.4	Accounting Roadmap v5
MMP5.3	Accounting Portal v4.4 (Hadar)
MMP5.4	Accounting Roadmap v6
MMP6.3	Accounting Portal v5 (Izar)
MMP6.4	Accounting Roadmap v7

# Schedule

DATE	EVENT
10/31/12	DMP3.1.x DMP3.2.x DMP3.3 MMP3.3 MMP3.4 (Fomalhaut release)
04/30/13	DMP4.1.x DMP4.2.x DMP4.3 MMP4.3 MMP4.4 (Giedi release)
10/30/13	DMP5.1.x DMP5.2.x DMP5.3 MMP5.3 MMP5.4 (Hadar release)
04/30/14	DMP6.1.x DMP6.2.x DMP6.3 MMP6.3 MMP6.4 (Izar release)

Figure 2: Release Cycle

Each release will be produced each 6 months.